## Sheet1
Phase | Macro Task | Micro Task | Operation Mode | Quantity | Rate (units/hr) | Estimated Time (hr) | Cumulative Time (days)
Phase 0: BOP & Riser Retrieval / pre rig move | BOP & Riser Retrieval / pre rig move | Pull Out Mule Shoe | N/A | 2365 | 424.6052 | 5.57 | 0.23
Phase 0: BOP & Riser Retrieval / pre rig move | BOP & Riser Retrieval / pre rig move | Lay_Dn_Cement_Head | N/A | 1 | 0.7 | 1.43 | 0.29
Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Rig_up_for_riser_handling | N/A | 1 | 0.16566 | 6.04 | 0.54
Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Unlatch_BOP | N/A | 1 | 1 | 1 | 0.58
Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Secure_Choke_Kill_Boost_Goosenecks | N/A | 1 | 0.25 | 4 | 0.75
Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | L_dn_dummy_riser_n_slip_jt | N/A | 1 | 0.5 | 2 | 0.83
Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Tripping_BOP | N/A | 78 | 3.1566 | 24.71 | 1.86
Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Receive_and_Park_BOP | N/A | 1 | 0.047619 | 21 | 2.74
Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Sea_Fasten_Prepare_for_rig_move | N/A | 1 | 0.2 | 5 | 2.95
Phase 0: BOP & Riser Retrieval / pre rig move | Sail to Well | Sail to Well | N/A | 280 | 6.9687 | 40.18 | 4.62
Phase 0: BOP & Riser Retrieval / pre rig move | DP Calibration | DP Calibration | N/A | 1 | 0.042553 | 23.5 | 5.6
Top Hole | Investigative Hole | Continue RIH 12-1/4'' IH BHA | N/A | 1057.5 | 424.6052 | 2.49 | 5.7
Top Hole | Investigative Hole | Drill 12-1/4'' IH Hole | N/A | 630 | 28.9714 | 21.75 | 6.61
Top Hole | Investigative Hole | Wiper Trip | N/A | 1 | 0.1597 | 6.26 | 6.87
Top Hole | Investigative Hole | Circulation | N/A | 602.6118 | 823.0366 | 0.73 | 6.9
Top Hole | Investigative Hole | POOH 12-1/4'' IH BHA | N/A | 2745 | 424.6052 | 6.46 | 7.17
Top Hole | Investigative Hole | Slip and Cut | N/A | 1 | 0.40126 | 2.49 | 7.28
Top Hole | Jet 36'' Casing | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 7.34
Top Hole | Jet 36'' Casing | Run Conductor Casing | Running In | 7 | 0.93961 | 7.45 | 7.65
Top Hole | Jet 36'' Casing | Install_Ball_Valves_Slope_Indicator_Latch_Mud_Mat | N/A | 1 | 0.53571 | 1.87 | 7.73
Top Hole | Jet 36'' Casing | Tripping_36_Casing_on_Landing_String | N/A | 1485 | 274.3454 | 5.41 | 7.96
Top Hole | Jet 36'' Casing | Tripping_36_Casing_on_Landing_String_OH | N/A | 630 | 46.6667 | 13.5 | 8.52
Top Hole | Jet 36'' Casing | Jet Conductor Casing | N/A | 1 | 9 | 0.11 | 8.52
Top Hole | Jet 36'' Casing | Wait on soaking | N/A | 1 | 12 | 0.08 | 8.53
Top Hole | Drill 26'' Hole | Drill 26'' | Rotate & Circulate | 550 | 14.3486 | 38.33 | 10.12
Top Hole | Drill 26'' Hole | Wiper Trip | N/A | 1 | 0.04143 | 24.14 | 11.13
Top Hole | Drill 26'' Hole | Circulate | N/A | 3096.1943 | 1428.5714 | 2.17 | 11.22
Top Hole | Drill 26'' Hole | POOH 26'' BHA | Pulling Out | 2745 | 424.6052 | 6.46 | 11.49
Top Hole | Drill 26'' Hole | Break Off BHA | N/A | 1 | 0.24399 | 4.1 | 11.66
Top Hole | Run 20'' Casing & Cement | Rig_up_for_Casing | N/A | 1 | 0.44444 | 2.25 | 11.75
Top Hole | Run 20'' Casing & Cement | Run_Check_Float_Fun_20_Casing | N/A | 1 | 0.44444 | 2.25 | 11.85
Top Hole | Run 20'' Casing & Cement | Run 20'' Casing | Running In | 53 | 3.1364 | 16.9 | 12.55
Top Hole | Run 20'' Casing & Cement | M_Up_HPWHH_Run_Inner_String_Engage_Cart_to_HPWHH | N/A | 1 | 0.23529 | 4.25 | 12.73
Top Hole | Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String | N/A | 1485 | 206.1859 | 7.2 | 13.03
Top Hole | Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | N/A | 630 | 132.7857 | 4.74 | 13.23
Top Hole | Run 20'' Casing & Cement | Cementing 20'' Casing | N/A | 1 | 0.16667 | 6 | 13.48
Top Hole | Run 20'' Casing & Cement | Wait on Cement | N/A | 1 | 0.083333 | 12 | 13.98
Top Hole | Run 20'' Casing & Cement | Release_Cart_from_HPWHH | N/A | 1 | 3.8904 | 0.26 | 13.99
Top Hole | Run 20'' Casing & Cement | POOH Cart Tool to surface | Pulling Out | 2115 | 424.6052 | 4.98 | 14.19
Phase 2: Surface Section | BOP Lowering | Rig_up_for_riser_handling | N/A | 1 | 0.16566 | 6.04 | 14.45
Phase 2: Surface Section | BOP Lowering | Run_BOP_Splash_Zone | N/A | 1 | 0.4 | 2.5 | 14.55
Phase 2: Surface Section | BOP Lowering | Run BOP on Riser | N/A | 78 | 3.1566 | 24.71 | 15.58
Phase 2: Surface Section | BOP Lowering | Pressure Test Choke, Kill, Boost & Conduit Lines | N/A | 5 | 0.49431 | 10.12 | 16
Phase 2: Surface Section | BOP Lowering | Run_Slip_Jt_Landing_Jt | N/A | 1 | 0.36364 | 2.75 | 16.12
Phase 2: Surface Section | BOP Lowering | Install_C_K_B_C_Goosenecks | N/A | 1 | 0.4 | 2.5 | 16.22
Phase 2: Surface Section | BOP Lowering | Pressure Test Choke, Kill & Boost Goosenecks | N/A | 1 | 0.49431 | 2.02 | 16.3
Phase 2: Surface Section | BOP Lowering | Install_Saddle_Loops_Engage_MRT | N/A | 1 | 0.30769 | 3.25 | 16.44
Phase 2: Surface Section | BOP Lowering | Land & Latch BOP. Carry Out Pick up and Slump Test | N/A | 1 | 0.66667 | 1.5 | 16.5
Phase 2: Surface Section | BOP Lowering | Pressure Test Connector. Stroke out Slip Jt & Lay Dn Landing Jt | N/A | 1 | 0.5 | 2 | 16.59
Phase 2: Surface Section | BOP Lowering | Install_Diverter | N/A | 1 | 0.28571 | 3.5 | 16.73
Phase 2: Surface Section | BOP Lowering | Rig Down Spider & Gimbal | N/A | 1 | 1 | 1 | 16.77
Intermediate Casing | RIH dumb iron BHA and Carry out LOT | slip_and_cut | N/A | 1 | 0.40126 | 2.49 | 16.88
Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 16.94
Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Surface Equipment Pressure Test | N/A | 1 | 0.4 | 2.5 | 17.05
Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Make up Dumb Iron BHA | N/A | 1 | 0.21835 | 4.58 | 17.24
Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Run 17-1/2'' BHA | N/A | 2695 | 424.6052 | 6.35 | 17.5
Intermediate Casing | RIH dumb iron BHA and Carry out LOT | BOP Pressure Test | N/A | 1 | 0.15385 | 6.5 | 17.77
Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Continue RIH with Wash Dn & Tag Cement | N/A | 30 | 147 | 0.2 | 17.78
Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Drill_Shoe_Track_LOT | N/A | 1 | 0.067608 | 14.79 | 18.4
Intermediate Casing | RIH dumb iron BHA and Carry out LOT | POOH | Pulling Out | 2750 | 424.6052 | 6.48 | 18.67
Intermediate Casing | Drill 12.25'' Pilot Hole | slip_and_cut | N/A | 1 | 0.40126 | 2.49 | 18.77
Intermediate Casing | Drill 12.25'' Pilot Hole | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 18.84
Intermediate Casing | Drill 12.25'' Pilot Hole | Surface Equipment Pressure Test | N/A | 1 | 0.4 | 2.5 | 18.94
Intermediate Casing | Drill 12.25'' Pilot Hole | Make up LWD BHA | N/A | 1 | 0.21835 | 4.58 | 19.13
Intermediate Casing | Drill 12.25'' Pilot Hole | Run 12.25'' BHA | N/A | 2695 | 424.6052 | 6.35 | 19.4
Intermediate Casing | Drill 12.25'' Pilot Hole | BOP Pressure Test | N/A | 1 | 0.15385 | 6.5 | 19.67
Intermediate Casing | Drill 12.25'' Pilot Hole | Continue RIH with Wash Dn & Tag Cement | N/A | 30 | 147 | 0.2 | 19.68
Intermediate Casing | Drill 12.25'' Pilot Hole | Drill_Shoe_Track_LOT | N/A | 1 | 0.067608 | 14.79 | 20.3
Intermediate Casing | Drill 12.25'' Pilot Hole | Fingerprint_Flow_Back | N/A | 1 | 1.3333 | 0.75 | 20.33
Intermediate Casing | Drill 12.25'' Pilot Hole | Drill 12.25'' | Rotate & Circulate | 363 | 7.3928 | 49.1 | 22.37
Intermediate Casing | Drill 12.25'' Pilot Hole | Coring at depth 2915 | N/A | 1 | 0.042568 | 23.49 | 23.35
Intermediate Casing | Drill 12.25'' Pilot Hole | POOH | Pulling Out | 2755 | 424.6052 | 6.49 | 23.62
Intermediate Casing | Wireline Logging | Basic Logs | N/A | 1 | 0.33333 | 3 | 23.75
Intermediate Casing | Enlarge Pilot Hole | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 23.81
Intermediate Casing | Enlarge Pilot Hole | Make up MWD BHA | N/A | 1 | 0.21835 | 4.58 | 24
Intermediate Casing | Enlarge Pilot Hole | Run 17.5'' BHA | N/A | 2745 | 424.6052 | 6.46 | 24.27
Intermediate Casing | Enlarge Pilot Hole | Enlarge 12.25'' Hole to 17.5'' | Rotate & Circulate | 373 | 31.1233 | 11.98 | 24.77
Intermediate Casing | Enlarge Pilot Hole | Wiper Trip | N/A | 1 | 0.2115 | 4.73 | 24.97
Intermediate Casing | Enlarge Pilot Hole | Circulate | N/A | 3201.1474 | 1223.9177 | 2.62 | 25.08
Intermediate Casing | Enlarge Pilot Hole | POOH | Pulling Out | 3118 | 424.6052 | 7.34 | 25.38
Intermediate Casing | Run 13.375'' Casing & Cement | Retrieve Wear Bush | N/A | 1 | 0.083597 | 11.96 | 25.88
Intermediate Casing | Run 13.375'' Casing & Cement | Rig_up_for_Casing | N/A | 1 | 0.44444 | 2.25 | 25.98
Intermediate Casing | Run 13.375'' Casing & Cement | Run_Check_Float_Fun_13.625_Casing | N/A | 1 | 0.5 | 2 | 26.06
Intermediate Casing | Run 13.375'' Casing & Cement | Run 13.375'' Casing | Running In | 84 | 10.8 | 7.78 | 26.38
Intermediate Casing | Run 13.375'' Casing & Cement | Tripping_Casing_on_Landing_String | N/A | 2115 | 206.1859 | 10.26 | 26.81
Intermediate Casing | Run 13.375'' Casing & Cement | Land_Latch_Casing_Indexing_Pick_up_test | N/A | 1 | 0.26316 | 3.8 | 26.97
Intermediate Casing | Run 13.375'' Casing & Cement | Cementing_13-3/8_in | N/A | 1 | 0.125 | 8 | 27.3
Intermediate Casing | Run 13.375'' Casing & Cement | Set_Seal_Assembly | N/A | 1 | 0.57143 | 1.75 | 27.38
Intermediate Casing | Run 13.375'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | N/A | 1 | 0.66667 | 1.5 | 27.44
Intermediate Casing | Run 13.375'' Casing & Cement | POOH PADPRT to surface | N/A | 2115 | 424.6052 | 4.98 | 27.65
Intermediate Casing | Run 13.375'' Casing & Cement | slip_and_cut | N/A | 1 | 0.40126 | 2.49 | 27.75
Intermediate Casing | Run 13.375'' Casing & Cement | Set Wear Bush at Wellhead | N/A | 1 | 0.083597 | 11.96 | 28.25
Phase 4: Production Section | Drill 12.25'' Hole | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 28.32
Phase 4: Production Section | Drill 12.25'' Hole | Lay_Dn_Cement_Head | N/A | 1 | 0.7 | 1.43 | 28.38
Phase 4: Production Section | Drill 12.25'' Hole | Make up LWD BHA | N/A | 1 | 0.21835 | 4.58 | 28.57
Phase 4: Production Section | Drill 12.25'' Hole | Run 12.25'' BHA | N/A | 2818 | 424.6052 | 6.64 | 28.84
Phase 4: Production Section | Drill 12.25'' Hole | BOP_Function_Test | N/A | 1 | 1.6667 | 0.6 | 28.87
Phase 4: Production Section | Drill 12.25'' Hole | Choke_Drill | N/A | 1 | 0.8 | 1.25 | 28.92
Phase 4: Production Section | Drill 12.25'' Hole | Continue RIH with Wash Dn & Tag Cement | N/A | 30 | 147 | 0.2 | 28.93
Phase 4: Production Section | Drill 12.25'' Hole | Drill_Shoe_Track_LOT | N/A | 1 | 0.067608 | 14.79 | 29.54
Phase 4: Production Section | Drill 12.25'' Hole | Fingerprint_Flow_Back | N/A | 1 | 1.3333 | 0.75 | 29.58
Phase 4: Production Section | Drill 12.25'' Hole | Drill 12.25'' | Rotate & Circulate | 797 | 7.3928 | 107.81 | 34.07
Phase 4: Production Section | Drill 12.25'' Hole | Coring at depth 3635 | N/A | 1 | 0.036185 | 27.64 | 35.22
Phase 4: Production Section | Drill 12.25'' Hole | wiper_trip | N/A | 1 | 0.097781 | 10.23 | 35.65
Phase 4: Production Section | Drill 12.25'' Hole | Circulate | N/A | 2933.5594 | 823.0366 | 3.56 | 35.79
Phase 4: Production Section | Drill 12.25'' Hole | POOH 12.25'' BHA to casing shoe | Pulling Out | 807 | 144.6351 | 5.58 | 36.03
Phase 4: Production Section | Drill 12.25'' Hole | POOH 12.25'' BHA to surface | Pulling Out | 2818 | 424.6052 | 6.64 | 36.3
Phase 4: Production Section | Drill 12.25'' Hole | Break Off BHA | N/A | 1 | 0.24399 | 4.1 | 36.47
Phase 4: Production Section | Wireline Logging | Basic Logs | N/A | 1 | 0.33333 | 3 | 36.6
Phase 4: Production Section | Wireline Logging | Roundtrip for logging | N/A | 1 | 0.067639 | 14.78 | 37.21
Phase 4: Production Section | Wireline Logging | Advance_Logging | N/A | 1 | 0.66667 | 1.5 | 37.28
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Roundtrip for Casing Lowering | N/A | 1 | 0.067639 | 14.78 | 37.89
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Retrieve Wear Bush | N/A | 1 | 0.083597 | 11.96 | 38.39
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 38.46
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Run_Check_Float_Fun_9.625_Casing | N/A | 1 | 0.5 | 2 | 38.54
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Run 9-5/8'' Casing | Running In | 151 | 10.8 | 13.98 | 39.12
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String | N/A | 1308 | 206.1859 | 6.34 | 39.39
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | N/A | 807 | 132.7857 | 6.08 | 39.64
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Cementing_9-5/8_in | N/A | 1 | 0.125 | 8 | 39.98
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Set_Seal_Assembly | N/A | 1 | 0.57143 | 1.75 | 40.05
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | N/A | 1 | 0.66667 | 1.5 | 40.11
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | POOH PADPRT to surface | N/A | 2115 | 424.6052 | 4.98 | 40.32
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | slip_and_cut | N/A | 1 | 0.40126 | 2.49 | 40.42
Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Set Wear Bush at Wellhead | N/A | 1 | 0.083597 | 11.96 | 40.92
Liner Casing | Drill 8.5'' Hole | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 40.99
Liner Casing | Drill 8.5'' Hole | Make up LWD BHA | N/A | 1 | 0.21835 | 4.58 | 41.18
Liner Casing | Drill 8.5'' Hole | Run 8.5'' BHA | N/A | 3625 | 424.6052 | 8.54 | 41.53
Liner Casing | Drill 8.5'' Hole | BOP_Pressure_Test | N/A | 1 | 0.15385 | 6.5 | 41.81
Liner Casing | Drill 8.5'' Hole | Choke_Drill | N/A | 1 | 0.8 | 1.25 | 41.86
Liner Casing | Drill 8.5'' Hole | Continue RIH with Wash Dn & Tag Cement | N/A | 30 | 147 | 0.2 | 41.87
Liner Casing | Drill 8.5'' Hole | Drill_Shoe_Track_LOT | N/A | 1 | 0.067608 | 14.79 | 42.48
Liner Casing | Drill 8.5'' Hole | Fingerprint_Flow_Back | N/A | 1 | 1.3333 | 0.75 | 42.51
Liner Casing | Drill 8.5'' Hole | Drill 8.5'' | Rotate & Circulate | 1090 | 7.3928 | 147.44 | 48.66
Liner Casing | Drill 8.5'' Hole | Coring at depth 4275 | N/A | 1 | 0.031877 | 31.37 | 49.96
Liner Casing | Drill 8.5'' Hole | Coring at depth 4925 | N/A | 1 | 0.02827 | 35.37 | 51.44
Liner Casing | Drill 8.5'' Hole | wiper_trip | N/A | 1 | 0.055004 | 18.18 | 52.2
Liner Casing | Drill 8.5'' Hole | Circulate | N/A | 2622.3601 | 288.5136 | 9.09 | 52.57
Liner Casing | Drill 8.5'' Hole | POOH 12.25'' BHA to casing shoe | Pulling Out | 1100 | 144.6351 | 7.61 | 52.89
Liner Casing | Drill 8.5'' Hole | POOH 12.25'' BHA to surface | Pulling Out | 3625 | 424.6052 | 8.54 | 53.25
Liner Casing | Drill 8.5'' Hole | Break Off BHA | N/A | 1 | 0.24399 | 4.1 | 53.42
Liner Casing | Wireline Logging | Basic Logs | N/A | 1 | 0.0083333 | 120 | 58.42
Liner Casing | Wireline Logging | Roundtrip for logging | N/A | 1 | 0.053929 | 18.54 | 59.19
Liner Casing | Wireline Logging | Advance_Logging | N/A | 1 | 0.010753 | 93 | 63.06
Liner Casing | Run 7'' Liner & Cement | Roundtrip for Casing Lowering | N/A | 1 | 0.053929 | 18.54 | 63.84
Liner Casing | Run 7'' Liner & Cement | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 63.9
Liner Casing | Run 7'' Liner & Cement | Run_Check_Float_Fun_7''_Liner | N/A | 1 | 0.5 | 2 | 63.99
Liner Casing | Run 7'' Liner & Cement | Run 7'' Liner | Running In | 105 | 10.8 | 9.72 | 64.39
Liner Casing | Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String | N/A | 2675 | 206.1859 | 12.97 | 64.93
Liner Casing | Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String_OH | N/A | 1100 | 132.7857 | 8.28 | 65.28
Liner Casing | Run 7'' Liner & Cement | Cementing_7'' Liner | N/A | 1 | 0.125 | 8 | 65.61
Liner Casing | Run 7'' Liner & Cement | Set_Liner_Hanger_Seal | N/A | 1 | 0.57143 | 1.75 | 65.68
Liner Casing | Run 7'' Liner & Cement | Release_Liner_Hanger_Running_Tool | N/A | 1 | 0.66667 | 1.5 | 65.75
Liner Casing | Run 7'' Liner & Cement | POOH Liner Hanger Running Tool to surface | N/A | 2115 | 424.6052 | 4.98 | 65.95
Liner Casing | Run 7'' Liner & Cement | slip_and_cut | N/A | 1 | 0.40126 | 2.49 | 66.06
Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | RIH Tandem Scraper from surface to Scraping depth | Running In | 3425 | 424.6052 | 8.07 | 66.39
Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Scrape Casing | N/A | 1600 | 144.6351 | 11.06 | 66.86
Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | POOH Tandem Scraping BHA | N/A | 5025 | 424.6052 | 11.83 | 67.35
Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Record CBL VDL Log | N/A | 1 | 0.041667 | 24 | 68.35
Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Run Mule Shoe for hermetical and inflow test | N/A | 5025 | 424.6052 | 11.83 | 68.84
Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Changeover Well Volume from WBM to sea water | N/A | 2622.3601 | 324.5778 | 8.08 | 69.18
Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Carry out Inflow & Hermetical Test | N/A | 1 | 0.14286 | 7 | 69.47