## Sheet1
| Phase | Macro Task | Micro Task | Quantity | Rate (units/hr) | Estimated Time (hr) | Estimated Time (days) | Cumulative Time (days)
0 | Phase 0: BOP & Riser Retrieval / pre rig move | BOP & Riser Retrieval / pre rig move | Pull Out Mule Shoe | 2365 | 424.6052 | 5.57 | 0.23208 | 0.23
1 | Phase 0: BOP & Riser Retrieval / pre rig move | BOP & Riser Retrieval / pre rig move | Lay_Dn_Cement_Head | 1 | 0.7 | 1.43 | 0.059583 | 0.29
2 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Rig_up_for_riser_handling | 1 | 0.16566 | 6.04 | 0.25167 | 0.54
3 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Unlatch_BOP | 1 | 1 | 1 | 0.041667 | 0.58
4 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Secure_Choke_Kill_Boost_Goosenecks | 1 | 0.25 | 4 | 0.16667 | 0.75
5 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | L_dn_dummy_riser_n_slip_jt | 1 | 0.5 | 2 | 0.083333 | 0.83
6 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Tripping_BOP | 103 | 3.1566 | 32.63 | 1.3596 | 2.19
7 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Receive_and_Park_BOP | 1 | 0.047619 | 21 | 0.875 | 3.07
8 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Sea_Fasten_Prepare_for_rig_move | 1 | 0.2 | 5 | 0.20833 | 3.28
9 | Phase 0: BOP & Riser Retrieval / pre rig move | Sail to Well | Sail to Well | 280 | 6.9687 | 40.18 | 1.6742 | 4.95
10 | Phase 0: BOP & Riser Retrieval / pre rig move | DP Calibration | DP Calibration | 1 | 0.042553 | 23.5 | 0.97917 | 5.93
11 | Top Hole | Investigative Hole | Continue RIH 12-1/4'' IH BHA | 1057.5 | 424.6052 | 2.49 | 0.10375 | 6.03
12 | Top Hole | Investigative Hole | Drill 12-1/4'' IH Hole | 630 | 28.9714 | 21.75 | 0.90625 | 6.94
13 | Top Hole | Investigative Hole | Wiper Trip | 1 | 0.1597 | 6.26 | 0.26083 | 7.2
14 | Top Hole | Investigative Hole | Circulation | 602.6118 | 823.0366 | 0.73 | 0.030417 | 7.23
15 | Top Hole | Investigative Hole | POOH 12-1/4'' IH BHA | 2745 | 424.6052 | 6.46 | 0.26917 | 7.5
16 | Top Hole | Investigative Hole | Slip and Cut | 1 | 0.40126 | 2.49 | 0.10375 | 7.61
17 | Top Hole | Drill 42'' Hole | Make Up MWD BHA | 1 | 0.21835 | 4.58 | 0.19083 | 7.8
18 | Top Hole | Drill 42'' Hole | Run 26'' x 42'' BHA | 2115 | 424.6052 | 4.98 | 0.2075 | 8
19 | Top Hole | Drill 42'' Hole | Drill 42'' | 80 | 14.8 | 5.41 | 0.22542 | 8.23
20 | Top Hole | Drill 42'' Hole | Circulate, POOH, Wait for Soaking & RIH | 1 | 4.6691 | 0.21 | 0.00875 | 8.24
21 | Top Hole | Drill 42'' Hole | Circulation | 1204.6305 | 23.8095 | 50.59 | 2.1079 | 10.35
22 | Top Hole | Drill 42'' Hole | POOH | 2195 | 424.6052 | 5.17 | 0.21542 | 10.56
23 | Top Hole | Run Conductor Casing | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.067083 | 10.63
24 | Top Hole | Run Conductor Casing | Run Conductor Casing | 7 | 0.93961 | 7.45 | 0.31042 | 10.94
25 | Top Hole | Run Conductor Casing | Install_Ball_Valves_Slope_Indicator_Latch_Mud_Mat | 1 | 0.53571 | 1.87 | 0.077917 | 11.02
26 | Top Hole | Run Conductor Casing | Tripping_36_Casing_on_Landing_String | 1485 | 274.3454 | 5.41 | 0.22542 | 11.24
27 | Top Hole | Run Conductor Casing | Tripping_36_Casing_on_Landing_String_OH | 630 | 46.6667 | 13.5 | 0.5625 | 11.8
28 | Top Hole | Run Conductor Casing | Circulation | 1 | 1 | 1 | 0.041667 | 11.85
29 | Top Hole | Run Conductor Casing | Cement Conductor Casing | 1 | 0.33333 | 3 | 0.125 | 11.97
30 | Top Hole | Run Conductor Casing | Wait on Cement | 1 | 0.055556 | 18 | 0.75 | 12.72
31 | Top Hole | Run Conductor Casing | Release Cart Tool and POOH | 2115 | 424.6052 | 4.98 | 0.2075 | 12.93
32 | Top Hole | Run Conductor Casing | B_Off_Cart_Tool_PO_Inner_String | 1 | 0.4 | 2.5 | 0.10417 | 13.03
33 | Top Hole | Drill 26'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.067083 | 13.1
34 | Top Hole | Drill 26'' Hole | Make Up Mud Motor, MWD BHA | 1 | 0.21835 | 4.58 | 0.19083 | 13.29
35 | Top Hole | Drill 26'' Hole | RIH 26'' BHA | 2145 | 424.6052 | 5.05 | 0.21042 | 13.5
36 | Top Hole | Drill 26'' Hole | RIH with wash down and Tag cement | 30 | 147 | 0.2 | 0.0083333 | 13.51
37 | Top Hole | Drill 26'' Hole | Drill Cement & clear rat hole | 50 | 5.6667 | 8.82 | 0.3675 | 13.88
38 | Top Hole | Drill 26'' Hole | Drill 26'' | 550 | 14.3486 | 38.33 | 1.5971 | 15.47
39 | Top Hole | Drill 26'' Hole | Wiper Trip | 1 | 0.04143 | 24.14 | 1.0058 | 16.48
40 | Top Hole | Drill 26'' Hole | Circulate | 3096.1943 | 1428.5714 | 2.17 | 0.090417 | 16.57
41 | Top Hole | Drill 26'' Hole | POOH 26'' BHA | 2745 | 424.6052 | 6.46 | 0.26917 | 16.84
42 | Top Hole | Drill 26'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17083 | 17.01
43 | Top Hole | Run 20'' Casing & Cement | Rig_up_for_Casing | 1 | 0.44444 | 2.25 | 0.09375 | 17.1
44 | Top Hole | Run 20'' Casing & Cement | Run_Check_Float_Fun_20_Casing | 1 | 0.44444 | 2.25 | 0.09375 | 17.2
45 | Top Hole | Run 20'' Casing & Cement | Run 20'' Casing | 53 | 3.1364 | 16.9 | 0.70417 | 17.9
46 | Top Hole | Run 20'' Casing & Cement | M_Up_HPWHH_Run_Inner_String_Engage_Cart_to_HPWHH | 1 | 0.23529 | 4.25 | 0.17708 | 18.08
47 | Top Hole | Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String | 1485 | 206.1859 | 7.2 | 0.3 | 18.38
48 | Top Hole | Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | 630 | 132.7857 | 4.74 | 0.1975 | 18.58
49 | Top Hole | Run 20'' Casing & Cement | Cementing 20'' Casing | 1 | 0.16667 | 6 | 0.25 | 18.83
50 | Top Hole | Run 20'' Casing & Cement | Wait on Cement | 1 | 0.083333 | 12 | 0.5 | 19.33
51 | Top Hole | Run 20'' Casing & Cement | Release_Cart_from_HPWHH | 1 | 3.8904 | 0.26 | 0.010833 | 19.34
52 | Top Hole | Run 20'' Casing & Cement | POOH Cart Tool to surface | 2115 | 424.6052 | 4.98 | 0.2075 | 19.55
53 | Phase 2: Surface Section | BOP Lowering | Rig_up_for_riser_handling | 1 | 0.16566 | 6.04 | 0.25167 | 19.8
54 | Phase 2: Surface Section | BOP Lowering | Run_BOP_Splash_Zone | 1 | 0.4 | 2.5 | 0.10417 | 19.9
55 | Phase 2: Surface Section | BOP Lowering | Run BOP on Riser | 78 | 3.1566 | 24.71 | 1.0296 | 20.93
56 | Phase 2: Surface Section | BOP Lowering | Pressure Test Choke, Kill, Boost & Conduit Lines | 5 | 0.49431 | 10.12 | 0.42167 | 21.35
57 | Phase 2: Surface Section | BOP Lowering | Run_Slip_Jt_Landing_Jt | 1 | 0.36364 | 2.75 | 0.11458 | 21.47
58 | Phase 2: Surface Section | BOP Lowering | Install_C_K_B_C_Goosenecks | 1 | 0.4 | 2.5 | 0.10417 | 21.57
59 | Phase 2: Surface Section | BOP Lowering | Pressure Test Choke, Kill & Boost Goosenecks | 1 | 0.49431 | 2.02 | 0.084167 | 21.66
60 | Phase 2: Surface Section | BOP Lowering | Install_Saddle_Loops_Engage_MRT | 1 | 0.30769 | 3.25 | 0.13542 | 21.79
61 | Phase 2: Surface Section | BOP Lowering | Land & Latch BOP. Carry Out Pick up and Slump Test | 1 | 0.66667 | 1.5 | 0.0625 | 21.85
62 | Phase 2: Surface Section | BOP Lowering | Pressure Test Connector. Stroke out Slip Jt & Lay Dn Landing Jt | 1 | 0.5 | 2 | 0.083333 | 21.94
63 | Phase 2: Surface Section | BOP Lowering | Install_Diverter | 1 | 0.28571 | 3.5 | 0.14583 | 22.08
64 | Phase 2: Surface Section | BOP Lowering | Rig Down Spider & Gimbal | 1 | 1 | 1 | 0.041667 | 22.12
65 | Intermediate Casing | RIH dumb iron BHA and Carry out LOT | slip_and_cut | 1 | 0.40126 | 2.49 | 0.10375 | 22.23
66 | Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.067083 | 22.29
67 | Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Surface Equipment Pressure Test | 1 | 0.4 | 2.5 | 0.10417 | 22.4
68 | Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Make up Dumb Iron BHA | 1 | 0.21835 | 4.58 | 0.19083 | 22.59
69 | Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Run 17-1/2'' BHA | 2695 | 424.6052 | 6.35 | 0.26458 | 22.85
70 | Intermediate Casing | RIH dumb iron BHA and Carry out LOT | BOP Pressure Test | 1 | 0.15385 | 6.5 | 0.27083 | 23.13
71 | Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.0083333 | 23.13
72 | Intermediate Casing | RIH dumb iron BHA and Carry out LOT | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.61625 | 23.75
73 | Intermediate Casing | RIH dumb iron BHA and Carry out LOT | POOH | 2750 | 424.6052 | 6.48 | 0.27 | 24.02
74 | Intermediate Casing | Drill 12.25'' Pilot Hole | slip_and_cut | 1 | 0.40126 | 2.49 | 0.10375 | 24.12
75 | Intermediate Casing | Drill 12.25'' Pilot Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.067083 | 24.19
76 | Intermediate Casing | Drill 12.25'' Pilot Hole | Surface Equipment Pressure Test | 1 | 0.4 | 2.5 | 0.10417 | 24.29
77 | Intermediate Casing | Drill 12.25'' Pilot Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19083 | 24.49
78 | Intermediate Casing | Drill 12.25'' Pilot Hole | Run 12.25'' BHA | 2695 | 424.6052 | 6.35 | 0.26458 | 24.75
79 | Intermediate Casing | Drill 12.25'' Pilot Hole | BOP Pressure Test | 1 | 0.15385 | 6.5 | 0.27083 | 25.02
80 | Intermediate Casing | Drill 12.25'' Pilot Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.0083333 | 25.03
81 | Intermediate Casing | Drill 12.25'' Pilot Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.61625 | 25.65
82 | Intermediate Casing | Drill 12.25'' Pilot Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03125 | 25.68
83 | Intermediate Casing | Drill 12.25'' Pilot Hole | Drill 12.25'' | 363 | 7.3928 | 49.1 | 2.0458 | 27.72
84 | Intermediate Casing | Drill 12.25'' Pilot Hole | Coring at depth 2915 | 1 | 0.042568 | 23.49 | 0.97875 | 28.7
85 | Intermediate Casing | Drill 12.25'' Pilot Hole | POOH | 2755 | 424.6052 | 6.49 | 0.27042 | 28.97
86 | Intermediate Casing | Wireline Logging | Basic Logs | 1 | 0.33333 | 3 | 0.125 | 29.1
87 | Intermediate Casing | Enlarge Pilot Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.067083 | 29.16
88 | Intermediate Casing | Enlarge Pilot Hole | Make up MWD BHA | 1 | 0.21835 | 4.58 | 0.19083 | 29.35
89 | Intermediate Casing | Enlarge Pilot Hole | Run 17.5'' BHA | 2745 | 424.6052 | 6.46 | 0.26917 | 29.62
90 | Intermediate Casing | Enlarge Pilot Hole | Enlarge 12.25'' Hole to 17.5'' | 373 | 31.1233 | 11.98 | 0.49917 | 30.12
91 | Intermediate Casing | Enlarge Pilot Hole | Wiper Trip | 1 | 0.2115 | 4.73 | 0.19708 | 30.32
92 | Intermediate Casing | Enlarge Pilot Hole | Circulate | 3201.1474 | 1223.9177 | 2.62 | 0.10917 | 30.43
93 | Intermediate Casing | Enlarge Pilot Hole | POOH | 3118 | 424.6052 | 7.34 | 0.30583 | 30.74
94 | Intermediate Casing | Run 13.375'' Casing & Cement | Retrieve Wear Bush | 1 | 0.083597 | 11.96 | 0.49833 | 31.23
95 | Intermediate Casing | Run 13.375'' Casing & Cement | Rig_up_for_Casing | 1 | 0.44444 | 2.25 | 0.09375 | 31.33
96 | Intermediate Casing | Run 13.375'' Casing & Cement | Run_Check_Float_Fun_13.625_Casing | 1 | 0.5 | 2 | 0.083333 | 31.41
97 | Intermediate Casing | Run 13.375'' Casing & Cement | Run 13.375'' Casing | 84 | 10.8 | 7.78 | 0.32417 | 31.74
98 | Intermediate Casing | Run 13.375'' Casing & Cement | Tripping_Casing_on_Landing_String | 2115 | 206.1859 | 10.26 | 0.4275 | 32.16
99 | Intermediate Casing | Run 13.375'' Casing & Cement | Land_Latch_Casing_Indexing_Pick_up_test | 1 | 0.26316 | 3.8 | 0.15833 | 32.32
100 | Intermediate Casing | Run 13.375'' Casing & Cement | Cementing_13-3/8_in | 1 | 0.125 | 8 | 0.33333 | 32.65
101 | Intermediate Casing | Run 13.375'' Casing & Cement | Set_Seal_Assembly | 1 | 0.57143 | 1.75 | 0.072917 | 32.73
102 | Intermediate Casing | Run 13.375'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | 1 | 0.66667 | 1.5 | 0.0625 | 32.79
103 | Intermediate Casing | Run 13.375'' Casing & Cement | POOH PADPRT to surface | 2115 | 424.6052 | 4.98 | 0.2075 | 33
104 | Intermediate Casing | Run 13.375'' Casing & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.10375 | 33.1
105 | Intermediate Casing | Run 13.375'' Casing & Cement | Set Wear Bush at Wellhead | 1 | 0.083597 | 11.96 | 0.49833 | 33.6
106 | Phase 4: Production Section | Drill 12.25'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.067083 | 33.67
107 | Phase 4: Production Section | Drill 12.25'' Hole | Lay_Dn_Cement_Head | 1 | 0.7 | 1.43 | 0.059583 | 33.73
108 | Phase 4: Production Section | Drill 12.25'' Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19083 | 33.92
109 | Phase 4: Production Section | Drill 12.25'' Hole | Run 12.25'' BHA | 2818 | 424.6052 | 6.64 | 0.27667 | 34.19
110 | Phase 4: Production Section | Drill 12.25'' Hole | BOP_Function_Test | 1 | 1.6667 | 0.6 | 0.025 | 34.22
111 | Phase 4: Production Section | Drill 12.25'' Hole | Choke_Drill | 1 | 0.8 | 1.25 | 0.052083 | 34.27
112 | Phase 4: Production Section | Drill 12.25'' Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.0083333 | 34.28
113 | Phase 4: Production Section | Drill 12.25'' Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.61625 | 34.9
114 | Phase 4: Production Section | Drill 12.25'' Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03125 | 34.93
115 | Phase 4: Production Section | Drill 12.25'' Hole | Drill 12.25'' | 797 | 7.3928 | 107.81 | 4.4921 | 39.42
116 | Phase 4: Production Section | Drill 12.25'' Hole | Coring at depth 3635 | 1 | 0.036185 | 27.64 | 1.1517 | 40.57
117 | Phase 4: Production Section | Drill 12.25'' Hole | wiper_trip | 1 | 0.097781 | 10.23 | 0.42625 | 41
118 | Phase 4: Production Section | Drill 12.25'' Hole | Circulate | 2933.5594 | 823.0366 | 3.56 | 0.14833 | 41.14
119 | Phase 4: Production Section | Drill 12.25'' Hole | POOH 12.25'' BHA to casing shoe | 807 | 144.6351 | 5.58 | 0.2325 | 41.38
120 | Phase 4: Production Section | Drill 12.25'' Hole | POOH 12.25'' BHA to surface | 2818 | 424.6052 | 6.64 | 0.27667 | 41.65
121 | Phase 4: Production Section | Drill 12.25'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17083 | 41.82
122 | Phase 4: Production Section | Wireline Logging | Basic Logs | 1 | 0.33333 | 3 | 0.125 | 41.95
123 | Phase 4: Production Section | Wireline Logging | Roundtrip for logging | 1 | 0.067639 | 14.78 | 0.61583 | 42.57
124 | Phase 4: Production Section | Wireline Logging | Advance_Logging | 1 | 0.66667 | 1.5 | 0.0625 | 42.63
125 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Roundtrip for Casing Lowering | 1 | 0.067639 | 14.78 | 0.61583 | 43.24
126 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Retrieve Wear Bush | 1 | 0.083597 | 11.96 | 0.49833 | 43.74
127 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.067083 | 43.81
128 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Run_Check_Float_Fun_9.625_Casing | 1 | 0.5 | 2 | 0.083333 | 43.89
129 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Run 9-5/8'' Casing | 151 | 10.8 | 13.98 | 0.5825 | 44.48
130 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String | 1308 | 206.1859 | 6.34 | 0.26417 | 44.74
131 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | 807 | 132.7857 | 6.08 | 0.25333 | 44.99
132 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Cementing_9-5/8_in | 1 | 0.125 | 8 | 0.33333 | 45.33
133 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Set_Seal_Assembly | 1 | 0.57143 | 1.75 | 0.072917 | 45.4
134 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | 1 | 0.66667 | 1.5 | 0.0625 | 45.46
135 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | POOH PADPRT to surface | 2115 | 424.6052 | 4.98 | 0.2075 | 45.67
136 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.10375 | 45.77
137 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Set Wear Bush at Wellhead | 1 | 0.083597 | 11.96 | 0.49833 | 46.27
138 | Liner Casing | Drill 8.5'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.067083 | 46.34
139 | Liner Casing | Drill 8.5'' Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19083 | 46.53
140 | Liner Casing | Drill 8.5'' Hole | Run 8.5'' BHA | 3625 | 424.6052 | 8.54 | 0.35583 | 46.88
141 | Liner Casing | Drill 8.5'' Hole | BOP_Pressure_Test | 1 | 0.15385 | 6.5 | 0.27083 | 47.16
142 | Liner Casing | Drill 8.5'' Hole | Choke_Drill | 1 | 0.8 | 1.25 | 0.052083 | 47.21
143 | Liner Casing | Drill 8.5'' Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.0083333 | 47.22
144 | Liner Casing | Drill 8.5'' Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.61625 | 47.83
145 | Liner Casing | Drill 8.5'' Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03125 | 47.86
146 | Liner Casing | Drill 8.5'' Hole | Drill 8.5'' | 1090 | 7.3928 | 147.44 | 6.1433 | 54.01
147 | Liner Casing | Drill 8.5'' Hole | Coring at depth 4275 | 1 | 0.031877 | 31.37 | 1.3071 | 55.31
148 | Liner Casing | Drill 8.5'' Hole | Coring at depth 4925 | 1 | 0.02827 | 35.37 | 1.4737 | 56.79
149 | Liner Casing | Drill 8.5'' Hole | wiper_trip | 1 | 0.055004 | 18.18 | 0.7575 | 57.55
150 | Liner Casing | Drill 8.5'' Hole | Circulate | 2622.3601 | 288.5136 | 9.09 | 0.37875 | 57.92
151 | Liner Casing | Drill 8.5'' Hole | POOH 12.25'' BHA to casing shoe | 1100 | 144.6351 | 7.61 | 0.31708 | 58.24
152 | Liner Casing | Drill 8.5'' Hole | POOH 12.25'' BHA to surface | 3625 | 424.6052 | 8.54 | 0.35583 | 58.6
153 | Liner Casing | Drill 8.5'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17083 | 58.77
154 | Liner Casing | Wireline Logging | Basic Logs | 1 | 0.0083333 | 120 | 5 | 63.77
155 | Liner Casing | Wireline Logging | Roundtrip for logging | 1 | 0.053929 | 18.54 | 0.7725 | 64.54
156 | Liner Casing | Wireline Logging | Advance_Logging | 1 | 0.010753 | 93 | 3.875 | 68.42
157 | Liner Casing | Run 7'' Liner & Cement | Roundtrip for Casing Lowering | 1 | 0.053929 | 18.54 | 0.7725 | 69.19
158 | Liner Casing | Run 7'' Liner & Cement | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.067083 | 69.26
159 | Liner Casing | Run 7'' Liner & Cement | Run_Check_Float_Fun_7''_Liner | 1 | 0.5 | 2 | 0.083333 | 69.34
160 | Liner Casing | Run 7'' Liner & Cement | Run 7'' Liner | 105 | 10.8 | 9.72 | 0.405 | 69.74
161 | Liner Casing | Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String | 2675 | 206.1859 | 12.97 | 0.54042 | 70.28
162 | Liner Casing | Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String_OH | 1100 | 132.7857 | 8.28 | 0.345 | 70.63
163 | Liner Casing | Run 7'' Liner & Cement | Cementing_7'' Liner | 1 | 0.125 | 8 | 0.33333 | 70.96
164 | Liner Casing | Run 7'' Liner & Cement | Set_Liner_Hanger_Seal | 1 | 0.57143 | 1.75 | 0.072917 | 71.04
165 | Liner Casing | Run 7'' Liner & Cement | Release_Liner_Hanger_Running_Tool | 1 | 0.66667 | 1.5 | 0.0625 | 71.1
166 | Liner Casing | Run 7'' Liner & Cement | POOH Liner Hanger Running Tool to surface | 2115 | 424.6052 | 4.98 | 0.2075 | 71.31
167 | Liner Casing | Run 7'' Liner & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.10375 | 71.41
168 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | RIH Tandem Scraper from surface to Scraping depth | 3425 | 424.6052 | 8.07 | 0.33625 | 71.75
169 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Scrape Casing | 1600 | 144.6351 | 11.06 | 0.46083 | 72.21
170 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | POOH Tandem Scraping BHA | 5025 | 424.6052 | 11.83 | 0.49292 | 72.7
171 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Record CBL VDL Log | 1 | 0.041667 | 24 | 1 | 73.7
172 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Run Mule Shoe for hermetical and inflow test | 5025 | 424.6052 | 11.83 | 0.49292 | 74.19
173 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Changeover Well Volume from WBM to sea water | 2622.3601 | 324.5778 | 8.08 | 0.33667 | 74.53
174 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Carry out Inflow & Hermetical Test | 1 | 7 | 0.14 | 0.0058333 | 74.54