## Sheet1
| Phase | Macro Task | Micro Task | Operation Mode | Quantity | Rate (units/hr) | Estimated Time (hr) | Cumulative Time (days)
0 | Phase 0: BOP & Riser Retrieval / pre rig move | BOP & Riser Retrieval / pre rig move | Pull Out Mule Shoe | N/A | 2365 | 424.6052 | 5.57 | 0.23
1 | Phase 0: BOP & Riser Retrieval / pre rig move | BOP & Riser Retrieval / pre rig move | Lay_Dn_Cement_Head | N/A | 1 | 0.7 | 1.43 | 0.29
2 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Rig_up_for_riser_handling | N/A | 1 | 0.16566 | 6.04 | 0.54
3 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Unlatch_BOP | N/A | 1 | 1 | 1 | 0.58
4 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Secure_Choke_Kill_Boost_Goosenecks | N/A | 1 | 0.25 | 4 | 0.75
5 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | L_dn_dummy_riser_n_slip_jt | N/A | 1 | 0.5 | 2 | 0.83
6 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Tripping_BOP | N/A | 78 | 3.1566 | 24.71 | 1.86
7 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Receive_and_Park_BOP | N/A | 1 | 0.047619 | 21 | 2.74
8 | Phase 0: BOP & Riser Retrieval / pre rig move | Pull Out BOP | Sea_Fasten_Prepare_for_rig_move | N/A | 1 | 0.2 | 5 | 2.95
9 | Phase 0: BOP & Riser Retrieval / pre rig move | Sail to Well | Sail to Well | N/A | 280 | 6.9687 | 40.18 | 4.62
10 | Phase 0: BOP & Riser Retrieval / pre rig move | DP Calibration | DP Calibration | N/A | 1 | 0.042553 | 23.5 | 5.6
11 | Top Hole | Investigative Hole | Continue RIH 12-1/4'' IH BHA | N/A | 1057.5 | 424.6052 | 2.49 | 5.7
12 | Top Hole | Investigative Hole | Drill 12-1/4'' IH Hole | N/A | 630 | 28.9714 | 21.75 | 6.61
13 | Top Hole | Investigative Hole | Wiper Trip | N/A | 1 | 0.1597 | 6.26 | 6.87
14 | Top Hole | Investigative Hole | Circulation | N/A | 602.6118 | 823.0366 | 0.73 | 6.9
15 | Top Hole | Investigative Hole | POOH 12-1/4'' IH BHA | N/A | 2745 | 424.6052 | 6.46 | 7.17
16 | Top Hole | Investigative Hole | Slip and Cut | N/A | 1 | 0.40126 | 2.49 | 7.28
17 | Top Hole | Jet 36'' Casing | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 7.34
18 | Top Hole | Jet 36'' Casing | Run Conductor Casing | Running In | 7 | 0.93961 | 7.45 | 7.65
19 | Top Hole | Jet 36'' Casing | Install_Ball_Valves_Slope_Indicator_Latch_Mud_Mat | N/A | 1 | 0.53571 | 1.87 | 7.73
20 | Top Hole | Jet 36'' Casing | Tripping_36_Casing_on_Landing_String | N/A | 1485 | 274.3454 | 5.41 | 7.96
21 | Top Hole | Jet 36'' Casing | Tripping_36_Casing_on_Landing_String_OH | N/A | 630 | 46.6667 | 13.5 | 8.52
22 | Top Hole | Jet 36'' Casing | Jet Conductor Casing | N/A | 1 | 9 | 0.11 | 8.52
23 | Top Hole | Jet 36'' Casing | Wait on soaking | N/A | 1 | 12 | 0.08 | 8.53
24 | Top Hole | Drill 26'' Hole | Drill 26'' | Rotate & Circulate | 550 | 14.3486 | 38.33 | 10.12
25 | Top Hole | Drill 26'' Hole | Wiper Trip | N/A | 1 | 0.04143 | 24.14 | 11.13
26 | Top Hole | Drill 26'' Hole | Circulate | N/A | 3096.1943 | 1428.5714 | 2.17 | 11.22
27 | Top Hole | Drill 26'' Hole | POOH 26'' BHA | Pulling Out | 2745 | 424.6052 | 6.46 | 11.49
28 | Top Hole | Drill 26'' Hole | Break Off BHA | N/A | 1 | 0.24399 | 4.1 | 11.66
29 | Top Hole | Run 20'' Casing & Cement | Rig_up_for_Casing | N/A | 1 | 0.44444 | 2.25 | 11.75
30 | Top Hole | Run 20'' Casing & Cement | Run_Check_Float_Fun_20_Casing | N/A | 1 | 0.44444 | 2.25 | 11.85
31 | Top Hole | Run 20'' Casing & Cement | Run 20'' Casing | Running In | 53 | 3.1364 | 16.9 | 12.55
32 | Top Hole | Run 20'' Casing & Cement | M_Up_HPWHH_Run_Inner_String_Engage_Cart_to_HPWHH | N/A | 1 | 0.23529 | 4.25 | 12.73
33 | Top Hole | Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String | N/A | 1485 | 206.1859 | 7.2 | 13.03
34 | Top Hole | Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | N/A | 630 | 132.7857 | 4.74 | 13.23
35 | Top Hole | Run 20'' Casing & Cement | Cementing 20'' Casing | N/A | 1 | 0.16667 | 6 | 13.48
36 | Top Hole | Run 20'' Casing & Cement | Wait on Cement | N/A | 1 | 0.083333 | 12 | 13.98
37 | Top Hole | Run 20'' Casing & Cement | Release_Cart_from_HPWHH | N/A | 1 | 3.8904 | 0.26 | 13.99
38 | Top Hole | Run 20'' Casing & Cement | POOH Cart Tool to surface | Pulling Out | 2115 | 424.6052 | 4.98 | 14.19
39 | Phase 2: Surface Section | BOP Lowering | Rig_up_for_riser_handling | N/A | 1 | 0.16566 | 6.04 | 14.45
40 | Phase 2: Surface Section | BOP Lowering | Run_BOP_Splash_Zone | N/A | 1 | 0.4 | 2.5 | 14.55
41 | Phase 2: Surface Section | BOP Lowering | Run BOP on Riser | N/A | 78 | 3.1566 | 24.71 | 15.58
42 | Phase 2: Surface Section | BOP Lowering | Pressure Test Choke, Kill, Boost & Conduit Lines | N/A | 5 | 0.49431 | 10.12 | 16
43 | Phase 2: Surface Section | BOP Lowering | Run_Slip_Jt_Landing_Jt | N/A | 1 | 0.36364 | 2.75 | 16.12
44 | Phase 2: Surface Section | BOP Lowering | Install_C_K_B_C_Goosenecks | N/A | 1 | 0.4 | 2.5 | 16.22
45 | Phase 2: Surface Section | BOP Lowering | Pressure Test Choke, Kill & Boost Goosenecks | N/A | 1 | 0.49431 | 2.02 | 16.3
46 | Phase 2: Surface Section | BOP Lowering | Install_Saddle_Loops_Engage_MRT | N/A | 1 | 0.30769 | 3.25 | 16.44
47 | Phase 2: Surface Section | BOP Lowering | Land & Latch BOP. Carry Out Pick up and Slump Test | N/A | 1 | 0.66667 | 1.5 | 16.5
48 | Phase 2: Surface Section | BOP Lowering | Pressure Test Connector. Stroke out Slip Jt & Lay Dn Landing Jt | N/A | 1 | 0.5 | 2 | 16.59
49 | Phase 2: Surface Section | BOP Lowering | Install_Diverter | N/A | 1 | 0.28571 | 3.5 | 16.73
50 | Phase 2: Surface Section | BOP Lowering | Rig Down Spider & Gimbal | N/A | 1 | 1 | 1 | 16.77
51 | Phase 4: Production Section | Drill 12.25'' Hole | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 16.84
52 | Phase 4: Production Section | Drill 12.25'' Hole | Lay_Dn_Cement_Head | N/A | 1 | 0.7 | 1.43 | 16.9
53 | Phase 4: Production Section | Drill 12.25'' Hole | Make up LWD BHA | N/A | 1 | 0.21835 | 4.58 | 17.09
54 | Phase 4: Production Section | Drill 12.25'' Hole | Run 12.25'' BHA | N/A | 2818 | 424.6052 | 6.64 | 17.37
55 | Phase 4: Production Section | Drill 12.25'' Hole | BOP_Function_Test | N/A | 1 | 1.6667 | 0.6 | 17.39
56 | Phase 4: Production Section | Drill 12.25'' Hole | Choke_Drill | N/A | 1 | 0.8 | 1.25 | 17.44
57 | Phase 4: Production Section | Drill 12.25'' Hole | Continue RIH with Wash Dn & Tag Cement | N/A | 30 | 147 | 0.2 | 17.45
58 | Phase 4: Production Section | Drill 12.25'' Hole | Drill_Shoe_Track_LOT | N/A | 1 | 0.067608 | 14.79 | 18.07
59 | Phase 4: Production Section | Drill 12.25'' Hole | Fingerprint_Flow_Back | N/A | 1 | 1.3333 | 0.75 | 18.1
60 | Phase 4: Production Section | Drill 12.25'' Hole | Drill 12.25'' | Rotate & Circulate | 797 | 7.3928 | 107.81 | 22.59
61 | Phase 4: Production Section | Drill 12.25'' Hole | Coring at depth 3635 | N/A | 1 | 0.036185 | 27.64 | 23.74
62 | Phase 4: Production Section | Drill 12.25'' Hole | wiper_trip | N/A | 1 | 0.097781 | 10.23 | 24.17
63 | Phase 4: Production Section | Drill 12.25'' Hole | Circulate | N/A | 2933.5594 | 823.0366 | 3.56 | 24.32
64 | Phase 4: Production Section | Drill 12.25'' Hole | POOH 12.25'' BHA to casing shoe | Pulling Out | 807 | 144.6351 | 5.58 | 24.55
65 | Phase 4: Production Section | Drill 12.25'' Hole | POOH 12.25'' BHA to surface | Pulling Out | 2818 | 424.6052 | 6.64 | 24.83
66 | Phase 4: Production Section | Drill 12.25'' Hole | Break Off BHA | N/A | 1 | 0.24399 | 4.1 | 25
67 | Phase 4: Production Section | Wireline Logging | Basic Logs | N/A | 1 | 0.33333 | 3 | 25.12
68 | Phase 4: Production Section | Wireline Logging | Roundtrip for logging | N/A | 1 | 0.067639 | 14.78 | 25.74
69 | Phase 4: Production Section | Wireline Logging | Advance_Logging | N/A | 1 | 0.66667 | 1.5 | 25.8
70 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Roundtrip for Casing Lowering | N/A | 1 | 0.067639 | 14.78 | 26.42
71 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Retrieve Wear Bush | N/A | 1 | 0.083597 | 11.96 | 26.92
72 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 26.98
73 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Run_Check_Float_Fun_9.625_Casing | N/A | 1 | 0.5 | 2 | 27.07
74 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Run 9-5/8'' Casing | Running In | 151 | 10.8 | 13.98 | 27.65
75 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String | N/A | 1308 | 206.1859 | 6.34 | 27.91
76 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | N/A | 807 | 132.7857 | 6.08 | 28.17
77 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Cementing_9-5/8_in | N/A | 1 | 0.125 | 8 | 28.5
78 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Set_Seal_Assembly | N/A | 1 | 0.57143 | 1.75 | 28.57
79 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | N/A | 1 | 0.66667 | 1.5 | 28.64
80 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | POOH PADPRT to surface | N/A | 2115 | 424.6052 | 4.98 | 28.84
81 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | slip_and_cut | N/A | 1 | 0.40126 | 2.49 | 28.95
82 | Phase 4: Production Section | Run 9-5/8'' Casing & Cement | Set Wear Bush at Wellhead | N/A | 1 | 0.083597 | 11.96 | 29.45
83 | Liner Casing | Drill 8.5'' Hole | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 29.51
84 | Liner Casing | Drill 8.5'' Hole | Make up LWD BHA | N/A | 1 | 0.21835 | 4.58 | 29.7
85 | Liner Casing | Drill 8.5'' Hole | Run 8.5'' BHA | N/A | 3625 | 424.6052 | 8.54 | 30.06
86 | Liner Casing | Drill 8.5'' Hole | BOP_Pressure_Test | N/A | 1 | 0.15385 | 6.5 | 30.33
87 | Liner Casing | Drill 8.5'' Hole | Choke_Drill | N/A | 1 | 0.8 | 1.25 | 30.38
88 | Liner Casing | Drill 8.5'' Hole | Continue RIH with Wash Dn & Tag Cement | N/A | 30 | 147 | 0.2 | 30.39
89 | Liner Casing | Drill 8.5'' Hole | Drill_Shoe_Track_LOT | N/A | 1 | 0.067608 | 14.79 | 31.01
90 | Liner Casing | Drill 8.5'' Hole | Fingerprint_Flow_Back | N/A | 1 | 1.3333 | 0.75 | 31.04
91 | Liner Casing | Drill 8.5'' Hole | Drill 8.5'' | Rotate & Circulate | 1090 | 7.3928 | 147.44 | 37.18
92 | Liner Casing | Drill 8.5'' Hole | Coring at depth 4275 | N/A | 1 | 0.031877 | 31.37 | 38.49
93 | Liner Casing | Drill 8.5'' Hole | Coring at depth 4925 | N/A | 1 | 0.02827 | 35.37 | 39.96
94 | Liner Casing | Drill 8.5'' Hole | wiper_trip | N/A | 1 | 0.055004 | 18.18 | 40.72
95 | Liner Casing | Drill 8.5'' Hole | Circulate | N/A | 2622.3601 | 288.5136 | 9.09 | 41.1
96 | Liner Casing | Drill 8.5'' Hole | POOH 12.25'' BHA to casing shoe | Pulling Out | 1100 | 144.6351 | 7.61 | 41.42
97 | Liner Casing | Drill 8.5'' Hole | POOH 12.25'' BHA to surface | Pulling Out | 3625 | 424.6052 | 8.54 | 41.77
98 | Liner Casing | Drill 8.5'' Hole | Break Off BHA | N/A | 1 | 0.24399 | 4.1 | 41.94
99 | Liner Casing | Wireline Logging | Basic Logs | N/A | 1 | 0.0083333 | 120 | 46.94
100 | Liner Casing | Wireline Logging | Roundtrip for logging | N/A | 1 | 0.053929 | 18.54 | 47.71
101 | Liner Casing | Wireline Logging | Advance_Logging | N/A | 1 | 0.010753 | 93 | 51.59
102 | Liner Casing | Run 7'' Liner & Cement | Roundtrip for Casing Lowering | N/A | 1 | 0.053929 | 18.54 | 52.36
103 | Liner Casing | Run 7'' Liner & Cement | Change_Pipe_Handler | N/A | 1 | 0.6219 | 1.61 | 52.43
104 | Liner Casing | Run 7'' Liner & Cement | Run_Check_Float_Fun_7''_Liner | N/A | 1 | 0.5 | 2 | 52.51
105 | Liner Casing | Run 7'' Liner & Cement | Run 7'' Liner | Running In | 105 | 10.8 | 9.72 | 52.92
106 | Liner Casing | Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String | N/A | 2675 | 206.1859 | 12.97 | 53.46
107 | Liner Casing | Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String_OH | N/A | 1100 | 132.7857 | 8.28 | 53.8
108 | Liner Casing | Run 7'' Liner & Cement | Cementing_7'' Liner | N/A | 1 | 0.125 | 8 | 54.14
109 | Liner Casing | Run 7'' Liner & Cement | Set_Liner_Hanger_Seal | N/A | 1 | 0.57143 | 1.75 | 54.21
110 | Liner Casing | Run 7'' Liner & Cement | Release_Liner_Hanger_Running_Tool | N/A | 1 | 0.66667 | 1.5 | 54.27
111 | Liner Casing | Run 7'' Liner & Cement | POOH Liner Hanger Running Tool to surface | N/A | 2115 | 424.6052 | 4.98 | 54.48
112 | Liner Casing | Run 7'' Liner & Cement | slip_and_cut | N/A | 1 | 0.40126 | 2.49 | 54.58
113 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | RIH Tandem Scraper from surface to Scraping depth | Running In | 3425 | 424.6052 | 8.07 | 54.92
114 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Scrape Casing | N/A | 1600 | 144.6351 | 11.06 | 55.38
115 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | POOH Tandem Scraping BHA | N/A | 5025 | 424.6052 | 11.83 | 55.87
116 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Record CBL VDL Log | N/A | 1 | 0.041667 | 24 | 56.87
117 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Run Mule Shoe for hermetical and inflow test | N/A | 5025 | 424.6052 | 11.83 | 57.37
118 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Changeover Well Volume from WBM to sea water | N/A | 2622.3601 | 324.5778 | 8.08 | 57.7
119 | Scraping, CBL-VDL & Hermetical | Scraping, CBL-VDL & Hermetical | Carry out Inflow & Hermetical Test | N/A | 1 | 0.14286 | 7 | 57.99