## Sheet1
Macro Task | Micro Task | Quantity | Rate (units/hr) | Estimated Time (hr) | Estimated Time (days) | Cumulative Time (days)
BOP & Riser Retrieval / pre rig move | Pull Out Mule Shoe | 2345 | 424.6052 | 5.52 | 0.23 | 0.23
BOP & Riser Retrieval / pre rig move | Lay_Dn_Cement_Head | 1 | 0.7 | 1.43 | 0.06 | 0.29
Pull Out BOP | Rig_up_for_riser_handling | 1 | 0.16566 | 6.04 | 0.25 | 0.54
Pull Out BOP | Unlatch_BOP | 1 | 1 | 1 | 0.04 | 0.58
Pull Out BOP | Secure_Choke_Kill_Boost_Goosenecks | 1 | 0.25 | 4 | 0.17 | 0.75
Pull Out BOP | L_dn_dummy_riser_n_slip_jt | 1 | 0.5 | 2 | 0.08 | 0.83
Pull Out BOP | Tripping_BOP | 77 | 3.1566 | 24.39 | 1.02 | 1.85
Pull Out BOP | Receive_and_Park_BOP | 1 | 0.047619 | 21 | 0.88 | 2.72
Pull Out BOP | Sea_Fasten_Prepare_for_rig_move | 1 | 0.2 | 5 | 0.21 | 2.93
Sail to Well | Sail to Well | 280 | 6.9687 | 40.18 | 1.67 | 4.61
DP Calibration | DP Calibration | 1 | 0.042553 | 23.5 | 0.98 | 5.59
Investigative Hole | Continue RIH 12-1/4'' IH BHA | 1047.5 | 424.6052 | 2.47 | 0.1 | 5.69
Investigative Hole | Drill 12-1/4'' IH Hole | 620 | 28.9714 | 21.4 | 0.89 | 6.58
Investigative Hole | Wiper Trip | 1 | 0.16221 | 6.16 | 0.26 | 6.84
Investigative Hole | Circulation | 593.0465 | 823.0366 | 0.72 | 0.03 | 6.87
Investigative Hole | POOH 12-1/4'' IH BHA | 2715 | 424.6052 | 6.39 | 0.27 | 7.13
Investigative Hole | Slip and Cut | 1 | 0.40126 | 2.49 | 0.1 | 7.24
Drill 42'' Hole | Make Up MWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 7.43
Drill 42'' Hole | Run 26'' x 42'' BHA | 2095 | 424.6052 | 4.93 | 0.21 | 7.63
Drill 42'' Hole | Drill 42'' | 80 | 14.8 | 5.41 | 0.23 | 7.86
Drill 42'' Hole | Circulate, POOH | 1 | 0.67 | 1.49 | 0.06 | 7.92
Drill 42'' Hole | Wait for Soaking & RIH | 1 | 0.25 | 4 | 0.17 | 8.09
Drill 42'' Hole | Circulation | 1201.8505 | 23.8095 | 50.48 | 2.1 | 10.19
Drill 42'' Hole | POOH | 2175 | 424.6052 | 5.12 | 0.21 | 10.4
Run Conductor Casing | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 10.47
Run Conductor Casing | Run Conductor Casing | 7 | 0.93961 | 7.45 | 0.31 | 10.78
Run Conductor Casing | Install_Ball_Valves_Slope_Indicator_Latch_Mud_Mat | 1 | 0.53571 | 1.87 | 0.08 | 10.86
Run Conductor Casing | Tripping_36_Casing_on_Landing_String | 1475 | 274.3454 | 5.38 | 0.22 | 11.08
Run Conductor Casing | Tripping_36_Casing_on_Landing_String_OH | 620 | 46.6667 | 13.29 | 0.55 | 11.64
Run Conductor Casing | Circulation | 1 | 1 | 1 | 0.04 | 11.68
Run Conductor Casing | Cement Conductor Casing | 1 | 0.33333 | 3 | 0.12 | 11.8
Run Conductor Casing | Wait on Cement | 1 | 0.055556 | 18 | 0.75 | 12.55
Run Conductor Casing | Release Cart Tool and POOH | 2095 | 424.6052 | 4.93 | 0.21 | 12.76
Run Conductor Casing | B_Off_Cart_Tool_PO_Inner_String | 1 | 0.4 | 2.5 | 0.1 | 12.86
Drill 26'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 12.93
Drill 26'' Hole | Make Up Mud Motor, MWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 13.12
Drill 26'' Hole | RIH 26'' BHA | 2125 | 424.6052 | 5 | 0.21 | 13.33
Drill 26'' Hole | RIH with wash down and Tag cement | 30 | 147 | 0.2 | 0.01 | 13.34
Drill 26'' Hole | Drill Cement & clear rat hole | 50 | 5.6667 | 8.82 | 0.37 | 13.71
Drill 26'' Hole | Drill 26'' | 540 | 14.3486 | 37.63 | 1.57 | 15.27
Drill 26'' Hole | Wiper Trip | 1 | 0.041917 | 23.86 | 0.99 | 16.27
Drill 26'' Hole | Circulate | 3048.9348 | 1428.5714 | 2.13 | 0.09 | 16.36
Drill 26'' Hole | POOH 26'' BHA | 2715 | 424.6052 | 6.39 | 0.27 | 16.62
Drill 26'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 16.79
Run 20'' Casing & Cement | Rig_up_for_Casing | 1 | 0.44444 | 2.25 | 0.09 | 16.89
Run 20'' Casing & Cement | Run_Check_Float_Fun_20_Casing | 1 | 0.44444 | 2.25 | 0.09 | 16.98
Run 20'' Casing & Cement | Run 20'' Casing | 52 | 3.1364 | 16.58 | 0.69 | 17.67
Run 20'' Casing & Cement | M_Up_HPWHH_Run_Inner_String_Engage_Cart_to_HPWHH | 1 | 0.23529 | 4.25 | 0.18 | 17.85
Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String | 1475 | 206.1859 | 7.15 | 0.3 | 18.15
Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | 620 | 132.7857 | 4.67 | 0.19 | 18.34
Run 20'' Casing & Cement | Cementing 20'' Casing | 1 | 0.16667 | 6 | 0.25 | 18.59
Run 20'' Casing & Cement | Wait on Cement | 1 | 0.083333 | 12 | 0.5 | 19.09
Run 20'' Casing & Cement | Release_Cart_from_HPWHH | 1 | 3.8904 | 0.26 | 0.01 | 19.1
Run 20'' Casing & Cement | POOH Cart Tool to surface | 2095 | 424.6052 | 4.93 | 0.21 | 19.31
BOP Lowering | Rig_up_for_riser_handling | 1 | 0.16566 | 6.04 | 0.25 | 19.56
BOP Lowering | Run_BOP_Splash_Zone | 1 | 0.4 | 2.5 | 0.1 | 19.66
BOP Lowering | Run BOP on Riser | 77 | 3.1566 | 24.39 | 1.02 | 20.68
BOP Lowering | Pressure Test Choke, Kill, Boost & Conduit Lines | 5 | 0.49431 | 10.12 | 0.42 | 21.1
BOP Lowering | Run_Slip_Jt_Landing_Jt | 1 | 0.36364 | 2.75 | 0.11 | 21.22
BOP Lowering | Install_C_K_B_C_Goosenecks | 1 | 0.4 | 2.5 | 0.1 | 21.32
BOP Lowering | Pressure Test Choke, Kill & Boost Goosenecks | 1 | 0.49431 | 2.02 | 0.08 | 21.41
BOP Lowering | Install_Saddle_Loops_Engage_MRT | 1 | 0.30769 | 3.25 | 0.14 | 21.54
BOP Lowering | Land & Latch BOP. Carry Out Pick up and Slump Test | 1 | 0.66667 | 1.5 | 0.06 | 21.6
BOP Lowering | Pressure Test Connector. Stroke out Slip Jt & Lay Dn Landing Jt | 1 | 0.5 | 2 | 0.08 | 21.69
BOP Lowering | Install_Diverter | 1 | 0.28571 | 3.5 | 0.15 | 21.83
BOP Lowering | Rig Down Spider & Gimbal | 1 | 1 | 1 | 0.04 | 21.87
RIH dumb iron BHA and Carry out LOT | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 21.98
RIH dumb iron BHA and Carry out LOT | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 22.05
RIH dumb iron BHA and Carry out LOT | Surface Equipment Pressure Test | 1 | 0.4 | 2.5 | 0.1 | 22.15
RIH dumb iron BHA and Carry out LOT | Make up Dumb Iron BHA | 1 | 0.21835 | 4.58 | 0.19 | 22.34
RIH dumb iron BHA and Carry out LOT | Run 17-1/2'' BHA | 2665 | 424.6052 | 6.28 | 0.26 | 22.6
RIH dumb iron BHA and Carry out LOT | BOP Pressure Test | 1 | 0.15385 | 6.5 | 0.27 | 22.87
RIH dumb iron BHA and Carry out LOT | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 22.88
RIH dumb iron BHA and Carry out LOT | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 23.5
RIH dumb iron BHA and Carry out LOT | POOH | 2720 | 424.6052 | 6.41 | 0.27 | 23.76
Drill 12.25'' Pilot Hole | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 23.87
Drill 12.25'' Pilot Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 23.93
Drill 12.25'' Pilot Hole | Surface Equipment Pressure Test | 1 | 0.4 | 2.5 | 0.1 | 24.04
Drill 12.25'' Pilot Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 24.23
Drill 12.25'' Pilot Hole | Run 12.25'' BHA | 2665 | 424.6052 | 6.28 | 0.26 | 24.49
Drill 12.25'' Pilot Hole | BOP Pressure Test | 1 | 0.15385 | 6.5 | 0.27 | 24.76
Drill 12.25'' Pilot Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 24.77
Drill 12.25'' Pilot Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 25.39
Drill 12.25'' Pilot Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 25.42
Drill 12.25'' Pilot Hole | Drill 12.25'' | 400 | 7.3928 | 54.11 | 2.25 | 27.67
Drill 12.25'' Pilot Hole | Coring at depth 2915 | 1 | 0.030427 | 32.87 | 1.37 | 29.04
Drill 12.25'' Pilot Hole | POOH | 2725 | 424.6052 | 6.42 | 0.27 | 29.31
Wireline Logging | Wireline Logging | 1 | 0.013889 | 72 | 3 | 32.31
Enlarge Pilot Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 32.38
Enlarge Pilot Hole | Make up MWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 32.57
Enlarge Pilot Hole | Run 17.5'' BHA | 2715 | 424.6052 | 6.39 | 0.27 | 32.83
Enlarge Pilot Hole | Enlarge 12.25'' Hole to 17.5'' | 410 | 31.1233 | 13.17 | 0.55 | 33.38
Enlarge Pilot Hole | Wiper Trip | 1 | 0.19858 | 5.04 | 0.21 | 33.59
Enlarge Pilot Hole | Circulate | 3202.3944 | 1223.9177 | 2.62 | 0.11 | 33.7
Enlarge Pilot Hole | POOH | 3125 | 424.6052 | 7.36 | 0.31 | 34.01
Run 13.375'' Casing & Cement | Retrieve Wear Bush | 1 | 0.08426 | 11.87 | 0.49 | 34.5
Run 13.375'' Casing & Cement | Rig_up_for_Casing | 1 | 0.44444 | 2.25 | 0.09 | 34.6
Run 13.375'' Casing & Cement | Run_Check_Float_Fun_13.625_Casing | 1 | 0.5 | 2 | 0.08 | 34.68
Run 13.375'' Casing & Cement | Run 13.375'' Casing | 86 | 10.8 | 7.96 | 0.33 | 35.01
Run 13.375'' Casing & Cement | Tripping_Casing_on_Landing_String | 2095 | 206.1859 | 10.16 | 0.42 | 35.43
Run 13.375'' Casing & Cement | Land_Latch_Casing_Indexing_Pick_up_test | 1 | 0.26316 | 3.8 | 0.16 | 35.59
Run 13.375'' Casing & Cement | Cementing_13-3/8_in | 1 | 0.125 | 8 | 0.33 | 35.93
Run 13.375'' Casing & Cement | Set_Seal_Assembly | 1 | 0.57143 | 1.75 | 0.07 | 36
Run 13.375'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | 1 | 0.66667 | 1.5 | 0.06 | 36.06
Run 13.375'' Casing & Cement | POOH PADPRT to surface | 2095 | 424.6052 | 4.93 | 0.21 | 36.27
Run 13.375'' Casing & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 36.37
Run 13.375'' Casing & Cement | Set Wear Bush at Wellhead | 1 | 0.08426 | 11.87 | 0.49 | 36.87
Drill 12.25'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 36.93
Drill 12.25'' Hole | Lay_Dn_Cement_Head | 1 | 0.7 | 1.43 | 0.06 | 36.99
Drill 12.25'' Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 37.18
Drill 12.25'' Hole | Run 12.25'' BHA | 2825 | 424.6052 | 6.65 | 0.28 | 37.46
Drill 12.25'' Hole | BOP_Function_Test | 1 | 1.6667 | 0.6 | 0.03 | 37.49
Drill 12.25'' Hole | Choke_Drill | 1 | 0.8 | 1.25 | 0.05 | 37.54
Drill 12.25'' Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 37.55
Drill 12.25'' Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 38.16
Drill 12.25'' Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 38.19
Drill 12.25'' Hole | Drill 12.25'' | 790 | 7.3928 | 106.86 | 4.45 | 42.65
Drill 12.25'' Hole | Coring at depth 3635 | 1 | 0.023565 | 42.44 | 1.77 | 44.41
Drill 12.25'' Hole | wiper_trip | 1 | 0.098496 | 10.15 | 0.42 | 44.84
Drill 12.25'' Hole | Circulate | 2920.4643 | 823.0366 | 3.55 | 0.15 | 44.99
Drill 12.25'' Hole | POOH 12.25'' BHA to casing shoe | 800 | 144.6351 | 5.53 | 0.23 | 45.22
Drill 12.25'' Hole | POOH 12.25'' BHA to surface | 2825 | 424.6052 | 6.65 | 0.28 | 45.49
Drill 12.25'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 45.66
Wireline Logging | Wireline Logging | 1 | 0.0083333 | 120 | 5 | 50.66
Run 9-5/8'' Casing & Cement | Roundtrip for Casing Lowering | 1 | 0.067485 | 14.82 | 0.62 | 51.28
Run 9-5/8'' Casing & Cement | Retrieve Wear Bush | 1 | 0.08426 | 11.87 | 0.49 | 51.78
Run 9-5/8'' Casing & Cement | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 51.84
Run 9-5/8'' Casing & Cement | Run_Check_Float_Fun_9.625_Casing | 1 | 0.5 | 2 | 0.08 | 51.93
Run 9-5/8'' Casing & Cement | Run 9-5/8'' Casing | 153 | 10.8 | 14.17 | 0.59 | 52.52
Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String | 1295 | 206.1859 | 6.28 | 0.26 | 52.78
Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | 800 | 132.7857 | 6.02 | 0.25 | 53.03
Run 9-5/8'' Casing & Cement | Cementing_9-5/8_in | 1 | 0.125 | 8 | 0.33 | 53.36
Run 9-5/8'' Casing & Cement | Set_Seal_Assembly | 1 | 0.57143 | 1.75 | 0.07 | 53.44
Run 9-5/8'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | 1 | 0.66667 | 1.5 | 0.06 | 53.5
Run 9-5/8'' Casing & Cement | POOH PADPRT to surface | 2095 | 424.6052 | 4.93 | 0.21 | 53.7
Run 9-5/8'' Casing & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 53.81
Run 9-5/8'' Casing & Cement | Set Wear Bush at Wellhead | 1 | 0.08426 | 11.87 | 0.49 | 54.3
Drill 8.5'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 54.37
Drill 8.5'' Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 54.56
Drill 8.5'' Hole | Run 8.5'' BHA | 3625 | 424.6052 | 8.54 | 0.36 | 54.92
Drill 8.5'' Hole | BOP_Pressure_Test | 1 | 0.15385 | 6.5 | 0.27 | 55.19
Drill 8.5'' Hole | Choke_Drill | 1 | 0.8 | 1.25 | 0.05 | 55.24
Drill 8.5'' Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 55.25
Drill 8.5'' Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 55.86
Drill 8.5'' Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 55.89
Drill 8.5'' Hole | Drill 8.5'' | 1090 | 7.3928 | 147.44 | 6.14 | 62.04
Drill 8.5'' Hole | Coring at depth 4275 | 1 | 0.02005 | 49.87 | 2.08 | 64.12
Drill 8.5'' Hole | Coring at depth 4925 | 1 | 0.018571 | 53.85 | 2.24 | 66.36
Drill 8.5'' Hole | wiper_trip | 1 | 0.055197 | 18.12 | 0.75 | 67.11
Drill 8.5'' Hole | Circulate | 2603.9931 | 288.5136 | 9.03 | 0.38 | 67.49
Drill 8.5'' Hole | POOH 12.25'' BHA to casing shoe | 1100 | 144.6351 | 7.61 | 0.32 | 67.81
Drill 8.5'' Hole | POOH 12.25'' BHA to surface | 3625 | 424.6052 | 8.54 | 0.36 | 68.16
Drill 8.5'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 68.33
Wireline Logging | Basic Logs | 1 | 0.010417 | 96 | 4 | 72.33
Wireline Logging | Roundtrip for logging | 1 | 0.053929 | 18.54 | 0.77 | 73.11
Wireline Logging | Advance_Logging | 1 | 0.010417 | 96 | 4 | 77.11
Run 7'' Liner & Cement | Roundtrip for Casing Lowering | 1 | 0.053929 | 18.54 | 0.77 | 77.88
Run 7'' Liner & Cement | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 77.95
Run 7'' Liner & Cement | Run_Check_Float_Fun_7''_Liner | 1 | 0.5 | 2 | 0.08 | 78.03
Run 7'' Liner & Cement | Run 7'' Liner | 105 | 10.8 | 9.72 | 0.41 | 78.43
Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String | 2675 | 206.1859 | 12.97 | 0.54 | 78.97
Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String_OH | 1100 | 132.7857 | 8.28 | 0.35 | 79.32
Run 7'' Liner & Cement | Cementing_7'' Liner | 1 | 0.125 | 8 | 0.33 | 79.65
Run 7'' Liner & Cement | Set_Liner_Hanger_Seal | 1 | 0.57143 | 1.75 | 0.07 | 79.73
Run 7'' Liner & Cement | Release_Liner_Hanger_Running_Tool | 1 | 0.66667 | 1.5 | 0.06 | 79.79
Run 7'' Liner & Cement | POOH Liner Hanger Running Tool to surface | 2095 | 424.6052 | 4.93 | 0.21 | 79.99
Run 7'' Liner & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 80.1
Scraping, CBL-VDL & Hermetical | RIH Tandem Scraper from surface to Scraping depth | 3425 | 424.6052 | 8.07 | 0.34 | 80.43
Scraping, CBL-VDL & Hermetical | Scrape Casing | 1600 | 144.6351 | 11.06 | 0.46 | 80.9
Scraping, CBL-VDL & Hermetical | POOH Tandem Scraping BHA | 5025 | 424.6052 | 11.83 | 0.49 | 81.39
Scraping, CBL-VDL & Hermetical | Record CBL VDL Log | 1 | 0.041667 | 24 | 1 | 82.39
Scraping, CBL-VDL & Hermetical | Run Mule Shoe for hermetical and inflow test | 5025 | 424.6052 | 11.83 | 0.49 | 82.88
Scraping, CBL-VDL & Hermetical | Changeover Well Volume from WBM to sea water | 2603.9931 | 324.5778 | 8.02 | 0.33 | 83.22
Scraping, CBL-VDL & Hermetical | Carry out Inflow & Hermetical Test | 1 | 0.14286 | 7 | 0.29 | 83.51