## Sheet1
Macro Task | Micro Task | Quantity | Rate (units/hr) | Estimated Time (hr) | Estimated Time (days) | Cumulative Time (days)
BOP & Riser Retrieval / pre rig move | Pull Out Mule Shoe | 2365 | 424.6052 | 5.57 | 0.23 | 0.23
BOP & Riser Retrieval / pre rig move | Lay_Dn_Cement_Head | 1 | 0.7 | 1.43 | 0.06 | 0.29
Pull Out BOP | Rig_up_for_riser_handling | 1 | 0.16566 | 6.04 | 0.25 | 0.54
Pull Out BOP | Unlatch_BOP | 1 | 1 | 1 | 0.04 | 0.58
Pull Out BOP | Secure_Choke_Kill_Boost_Goosenecks | 1 | 0.25 | 4 | 0.17 | 0.75
Pull Out BOP | L_dn_dummy_riser_n_slip_jt | 1 | 0.5 | 2 | 0.08 | 0.83
Pull Out BOP | Tripping_BOP | 78 | 3.1566 | 24.71 | 1.03 | 1.86
Pull Out BOP | Receive_and_Park_BOP | 1 | 0.047619 | 21 | 0.88 | 2.74
Pull Out BOP | Sea_Fasten_Prepare_for_rig_move | 1 | 0.2 | 5 | 0.21 | 2.95
Sail to Well | Sail to Well | 280 | 6.9687 | 40.18 | 1.67 | 4.62
DP Calibration | DP Calibration | 1 | 0.042553 | 23.5 | 0.98 | 5.6
Investigative Hole | Continue RIH 12-1/4'' IH BHA | 1057.5 | 424.6052 | 2.49 | 0.1 | 5.7
Investigative Hole | Drill 12-1/4'' IH Hole | 630 | 28.9714 | 21.75 | 0.91 | 6.61
Investigative Hole | Wiper Trip | 1 | 0.1597 | 6.26 | 0.26 | 6.87
Investigative Hole | Circulation | 602.6118 | 823.0366 | 0.73 | 0.03 | 6.9
Investigative Hole | POOH 12-1/4'' IH BHA | 2745 | 424.6052 | 6.46 | 0.27 | 7.17
Investigative Hole | Slip and Cut | 1 | 0.40126 | 2.49 | 0.1 | 7.28
Drill 42'' Hole | Make Up MWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 7.47
Drill 42'' Hole | Run 26'' x 42'' BHA | 2115 | 424.6052 | 4.98 | 0.21 | 7.67
Drill 42'' Hole | Drill 42'' | 80 | 14.8 | 5.41 | 0.23 | 7.9
Drill 42'' Hole | Circulate, POOH | 1 | 0.66912 | 1.49 | 0.06 | 7.96
Drill 42'' Hole | Wait for Soaking & RIH | 1 | 0.25 | 4 | 0.17 | 8.13
Drill 42'' Hole | Circulation | 1204.6305 | 23.8095 | 50.59 | 2.11 | 10.24
Drill 42'' Hole | POOH | 2195 | 424.6052 | 5.17 | 0.22 | 10.45
Run Conductor Casing | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 10.52
Run Conductor Casing | Run Conductor Casing | 7 | 0.93961 | 7.45 | 0.31 | 10.83
Run Conductor Casing | Install_Ball_Valves_Slope_Indicator_Latch_Mud_Mat | 1 | 0.53571 | 1.87 | 0.08 | 10.91
Run Conductor Casing | Tripping_36_Casing_on_Landing_String | 1485 | 274.3454 | 5.41 | 0.23 | 11.13
Run Conductor Casing | Tripping_36_Casing_on_Landing_String_OH | 630 | 46.6667 | 13.5 | 0.56 | 11.69
Run Conductor Casing | Circulation | 1 | 1 | 1 | 0.04 | 11.74
Run Conductor Casing | Cement Conductor Casing | 1 | 0.33333 | 3 | 0.12 | 11.86
Run Conductor Casing | Wait on Cement | 1 | 0.055556 | 18 | 0.75 | 12.61
Run Conductor Casing | Release Cart Tool and POOH | 2115 | 424.6052 | 4.98 | 0.21 | 12.82
Run Conductor Casing | B_Off_Cart_Tool_PO_Inner_String | 1 | 0.4 | 2.5 | 0.1 | 12.92
Drill 26'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 12.99
Drill 26'' Hole | Make Up Mud Motor, MWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 13.18
Drill 26'' Hole | RIH 26'' BHA | 2145 | 424.6052 | 5.05 | 0.21 | 13.39
Drill 26'' Hole | RIH with wash down and Tag cement | 30 | 147 | 0.2 | 0.01 | 13.4
Drill 26'' Hole | Drill Cement & clear rat hole | 50 | 5.6667 | 8.82 | 0.37 | 13.77
Drill 26'' Hole | Drill 26'' | 550 | 14.3486 | 38.33 | 1.6 | 15.36
Drill 26'' Hole | Wiper Trip | 1 | 0.04143 | 24.14 | 1.01 | 16.37
Drill 26'' Hole | Circulate | 3096.1943 | 1428.5714 | 2.17 | 0.09 | 16.46
Drill 26'' Hole | POOH 26'' BHA | 2745 | 424.6052 | 6.46 | 0.27 | 16.73
Drill 26'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 16.9
Run 20'' Casing & Cement | Rig_up_for_Casing | 1 | 0.44444 | 2.25 | 0.09 | 16.99
Run 20'' Casing & Cement | Run_Check_Float_Fun_20_Casing | 1 | 0.44444 | 2.25 | 0.09 | 17.09
Run 20'' Casing & Cement | Run 20'' Casing | 53 | 3.1364 | 16.9 | 0.7 | 17.79
Run 20'' Casing & Cement | M_Up_HPWHH_Run_Inner_String_Engage_Cart_to_HPWHH | 1 | 0.23529 | 4.25 | 0.18 | 17.97
Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String | 1485 | 206.1859 | 7.2 | 0.3 | 18.27
Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | 630 | 132.7857 | 4.74 | 0.2 | 18.47
Run 20'' Casing & Cement | Cementing 20'' Casing | 1 | 0.16667 | 6 | 0.25 | 18.72
Run 20'' Casing & Cement | Wait on Cement | 1 | 0.083333 | 12 | 0.5 | 19.22
Run 20'' Casing & Cement | Release_Cart_from_HPWHH | 1 | 3.8904 | 0.26 | 0.01 | 19.23
Run 20'' Casing & Cement | POOH Cart Tool to surface | 2115 | 424.6052 | 4.98 | 0.21 | 19.44
BOP Lowering | Rig_up_for_riser_handling | 1 | 0.16566 | 6.04 | 0.25 | 19.69
BOP Lowering | Run_BOP_Splash_Zone | 1 | 0.4 | 2.5 | 0.1 | 19.79
BOP Lowering | Run BOP on Riser | 78 | 3.1566 | 24.71 | 1.03 | 20.82
BOP Lowering | Pressure Test Choke, Kill, Boost & Conduit Lines | 5 | 0.49431 | 10.12 | 0.42 | 21.24
BOP Lowering | Run_Slip_Jt_Landing_Jt | 1 | 0.36364 | 2.75 | 0.11 | 21.36
BOP Lowering | Install_C_K_B_C_Goosenecks | 1 | 0.4 | 2.5 | 0.1 | 21.46
BOP Lowering | Pressure Test Choke, Kill & Boost Goosenecks | 1 | 0.49431 | 2.02 | 0.08 | 21.55
BOP Lowering | Install_Saddle_Loops_Engage_MRT | 1 | 0.30769 | 3.25 | 0.14 | 21.68
BOP Lowering | Land & Latch BOP. Carry Out Pick up and Slump Test | 1 | 0.66667 | 1.5 | 0.06 | 21.74
BOP Lowering | Pressure Test Connector. Stroke out Slip Jt & Lay Dn Landing Jt | 1 | 0.5 | 2 | 0.08 | 21.83
BOP Lowering | Install_Diverter | 1 | 0.28571 | 3.5 | 0.15 | 21.97
BOP Lowering | Rig Down Spider & Gimbal | 1 | 1 | 1 | 0.04 | 22.01
RIH dumb iron BHA and Carry out LOT | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 22.12
RIH dumb iron BHA and Carry out LOT | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 22.18
RIH dumb iron BHA and Carry out LOT | Surface Equipment Pressure Test | 1 | 0.4 | 2.5 | 0.1 | 22.29
RIH dumb iron BHA and Carry out LOT | Make up Dumb Iron BHA | 1 | 0.21835 | 4.58 | 0.19 | 22.48
RIH dumb iron BHA and Carry out LOT | Run 17-1/2'' BHA | 2695 | 424.6052 | 6.35 | 0.26 | 22.74
RIH dumb iron BHA and Carry out LOT | BOP Pressure Test | 1 | 0.15385 | 6.5 | 0.27 | 23.02
RIH dumb iron BHA and Carry out LOT | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 23.02
RIH dumb iron BHA and Carry out LOT | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 23.64
RIH dumb iron BHA and Carry out LOT | POOH | 2750 | 424.6052 | 6.48 | 0.27 | 23.91
Drill 12.25'' Pilot Hole | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 24.01
Drill 12.25'' Pilot Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 24.08
Drill 12.25'' Pilot Hole | Surface Equipment Pressure Test | 1 | 0.4 | 2.5 | 0.1 | 24.18
Drill 12.25'' Pilot Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 24.38
Drill 12.25'' Pilot Hole | Run 12.25'' BHA | 2695 | 424.6052 | 6.35 | 0.26 | 24.64
Drill 12.25'' Pilot Hole | BOP Pressure Test | 1 | 0.15385 | 6.5 | 0.27 | 24.91
Drill 12.25'' Pilot Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 24.92
Drill 12.25'' Pilot Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 25.54
Drill 12.25'' Pilot Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 25.57
Drill 12.25'' Pilot Hole | Drill 12.25'' | 363 | 7.3928 | 49.1 | 2.05 | 27.61
Drill 12.25'' Pilot Hole | Coring at depth 2915 | 1 | 0.032772 | 30.51 | 1.27 | 28.88
Drill 12.25'' Pilot Hole | POOH | 2755 | 424.6052 | 6.49 | 0.27 | 29.15
Wireline Logging | Wireline Logging | 1 | 0.013889 | 72 | 3 | 32.15
Enlarge Pilot Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 32.22
Enlarge Pilot Hole | Make up MWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 32.41
Enlarge Pilot Hole | Run 17.5'' BHA | 2745 | 424.6052 | 6.46 | 0.27 | 32.68
Enlarge Pilot Hole | Enlarge 12.25'' Hole to 17.5'' | 373 | 31.1233 | 11.98 | 0.5 | 33.18
Enlarge Pilot Hole | Wiper Trip | 1 | 0.2115 | 4.73 | 0.2 | 33.38
Enlarge Pilot Hole | Circulate | 3201.1474 | 1223.9177 | 2.62 | 0.11 | 33.49
Enlarge Pilot Hole | POOH | 3118 | 424.6052 | 7.34 | 0.31 | 33.79
Run 13.375'' Casing & Cement | Retrieve Wear Bush | 1 | 0.083597 | 11.96 | 0.5 | 34.29
Run 13.375'' Casing & Cement | Rig_up_for_Casing | 1 | 0.44444 | 2.25 | 0.09 | 34.39
Run 13.375'' Casing & Cement | Run_Check_Float_Fun_13.625_Casing | 1 | 0.5 | 2 | 0.08 | 34.47
Run 13.375'' Casing & Cement | Run 13.375'' Casing | 84 | 10.8 | 7.78 | 0.32 | 34.79
Run 13.375'' Casing & Cement | Tripping_Casing_on_Landing_String | 2115 | 206.1859 | 10.26 | 0.43 | 35.22
Run 13.375'' Casing & Cement | Land_Latch_Casing_Indexing_Pick_up_test | 1 | 0.26316 | 3.8 | 0.16 | 35.38
Run 13.375'' Casing & Cement | Cementing_13-3/8_in | 1 | 0.125 | 8 | 0.33 | 35.71
Run 13.375'' Casing & Cement | Set_Seal_Assembly | 1 | 0.57143 | 1.75 | 0.07 | 35.78
Run 13.375'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | 1 | 0.66667 | 1.5 | 0.06 | 35.85
Run 13.375'' Casing & Cement | POOH PADPRT to surface | 2115 | 424.6052 | 4.98 | 0.21 | 36.05
Run 13.375'' Casing & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 36.16
Run 13.375'' Casing & Cement | Set Wear Bush at Wellhead | 1 | 0.083597 | 11.96 | 0.5 | 36.66
Drill 12.25'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 36.72
Drill 12.25'' Hole | Lay_Dn_Cement_Head | 1 | 0.7 | 1.43 | 0.06 | 36.78
Drill 12.25'' Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 36.97
Drill 12.25'' Hole | Run 12.25'' BHA | 2818 | 424.6052 | 6.64 | 0.28 | 37.25
Drill 12.25'' Hole | BOP_Function_Test | 1 | 1.6667 | 0.6 | 0.03 | 37.28
Drill 12.25'' Hole | Choke_Drill | 1 | 0.8 | 1.25 | 0.05 | 37.33
Drill 12.25'' Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 37.34
Drill 12.25'' Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 37.95
Drill 12.25'' Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 37.98
Drill 12.25'' Hole | Drill 12.25'' | 797 | 7.3928 | 107.81 | 4.49 | 42.48
Drill 12.25'' Hole | Coring at depth 3635 | 1 | 0.023575 | 42.42 | 1.77 | 44.24
Drill 12.25'' Hole | wiper_trip | 1 | 0.097781 | 10.23 | 0.43 | 44.67
Drill 12.25'' Hole | Circulate | 2933.5594 | 823.0366 | 3.56 | 0.15 | 44.82
Drill 12.25'' Hole | POOH 12.25'' BHA to casing shoe | 807 | 144.6351 | 5.58 | 0.23 | 45.05
Drill 12.25'' Hole | POOH 12.25'' BHA to surface | 2818 | 424.6052 | 6.64 | 0.28 | 45.33
Drill 12.25'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 45.5
Wireline Logging | Wireline Logging | 1 | 0.010417 | 96 | 4 | 49.5
Wireline Logging | Roundtrip for logging | 1 | 0.067639 | 14.78 | 0.62 | 50.11
Wireline Logging | Wireline_Logging_part_2 | 1 | 0.010417 | 96 | 4 | 54.11
Run 9-5/8'' Casing & Cement | Roundtrip for Casing Lowering | 1 | 0.067639 | 14.78 | 0.62 | 54.73
Run 9-5/8'' Casing & Cement | Retrieve Wear Bush | 1 | 0.083597 | 11.96 | 0.5 | 55.23
Run 9-5/8'' Casing & Cement | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 55.3
Run 9-5/8'' Casing & Cement | Run_Check_Float_Fun_9.625_Casing | 1 | 0.5 | 2 | 0.08 | 55.38
Run 9-5/8'' Casing & Cement | Run 9-5/8'' Casing | 151 | 10.8 | 13.98 | 0.58 | 55.96
Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String | 1308 | 206.1859 | 6.34 | 0.26 | 56.23
Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | 807 | 132.7857 | 6.08 | 0.25 | 56.48
Run 9-5/8'' Casing & Cement | Cementing_9-5/8_in | 1 | 0.125 | 8 | 0.33 | 56.81
Run 9-5/8'' Casing & Cement | Set_Seal_Assembly | 1 | 0.57143 | 1.75 | 0.07 | 56.89
Run 9-5/8'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | 1 | 0.66667 | 1.5 | 0.06 | 56.95
Run 9-5/8'' Casing & Cement | POOH PADPRT to surface | 2115 | 424.6052 | 4.98 | 0.21 | 57.16
Run 9-5/8'' Casing & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 57.26
Run 9-5/8'' Casing & Cement | Set Wear Bush at Wellhead | 1 | 0.083597 | 11.96 | 0.5 | 57.76
Drill 8.5'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 57.82
Drill 8.5'' Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 58.02
Drill 8.5'' Hole | Run 8.5'' BHA | 3625 | 424.6052 | 8.54 | 0.36 | 58.37
Drill 8.5'' Hole | BOP_Pressure_Test | 1 | 0.15385 | 6.5 | 0.27 | 58.64
Drill 8.5'' Hole | Choke_Drill | 1 | 0.8 | 1.25 | 0.05 | 58.69
Drill 8.5'' Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 58.7
Drill 8.5'' Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 59.32
Drill 8.5'' Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 59.35
Drill 8.5'' Hole | Drill 8.5'' | 1090 | 7.3928 | 147.44 | 6.14 | 65.49
Drill 8.5'' Hole | Coring at depth 4275 | 1 | 0.020044 | 49.89 | 2.08 | 67.57
Drill 8.5'' Hole | Coring at depth 4925 | 1 | 0.018565 | 53.86 | 2.24 | 69.82
Drill 8.5'' Hole | wiper_trip | 1 | 0.055004 | 18.18 | 0.76 | 70.57
Drill 8.5'' Hole | Circulate | 2622.3601 | 288.5136 | 9.09 | 0.38 | 70.95
Drill 8.5'' Hole | POOH 12.25'' BHA to casing shoe | 1100 | 144.6351 | 7.61 | 0.32 | 71.27
Drill 8.5'' Hole | POOH 12.25'' BHA to surface | 3625 | 424.6052 | 8.54 | 0.36 | 71.63
Drill 8.5'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 71.8
Wireline Logging | Basic Logs | 1 | 0.010417 | 96 | 4 | 75.8
Wireline Logging | Roundtrip for logging | 1 | 0.053929 | 18.54 | 0.77 | 76.57
Wireline Logging | Advance_Logging | 1 | 0.010417 | 96 | 4 | 80.57
Run 7'' Liner & Cement | Roundtrip for Casing Lowering | 1 | 0.053929 | 18.54 | 0.77 | 81.34
Run 7'' Liner & Cement | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 81.41
Run 7'' Liner & Cement | Run_Check_Float_Fun_7''_Liner | 1 | 0.5 | 2 | 0.08 | 81.49
Run 7'' Liner & Cement | Run 7'' Liner | 105 | 10.8 | 9.72 | 0.41 | 81.9
Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String | 2675 | 206.1859 | 12.97 | 0.54 | 82.44
Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String_OH | 1100 | 132.7857 | 8.28 | 0.35 | 82.78
Run 7'' Liner & Cement | Cementing_7'' Liner | 1 | 0.125 | 8 | 0.33 | 83.12
Run 7'' Liner & Cement | Set_Liner_Hanger_Seal | 1 | 0.57143 | 1.75 | 0.07 | 83.19
Run 7'' Liner & Cement | Release_Liner_Hanger_Running_Tool | 1 | 0.66667 | 1.5 | 0.06 | 83.25
Run 7'' Liner & Cement | POOH Liner Hanger Running Tool to surface | 2115 | 424.6052 | 4.98 | 0.21 | 83.46
Run 7'' Liner & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 83.56
Scraping, CBL-VDL & Hermetical | RIH Tandem Scraper from surface to Scraping depth | 3425 | 424.6052 | 8.07 | 0.34 | 83.9
Scraping, CBL-VDL & Hermetical | Scrape Casing | 1600 | 144.6351 | 11.06 | 0.46 | 84.36
Scraping, CBL-VDL & Hermetical | POOH Tandem Scraping BHA | 5025 | 424.6052 | 11.83 | 0.49 | 84.85
Scraping, CBL-VDL & Hermetical | Record CBL VDL Log | 1 | 0.041667 | 24 | 1 | 85.85
Scraping, CBL-VDL & Hermetical | Run Mule Shoe for hermetical and inflow test | 5025 | 424.6052 | 11.83 | 0.49 | 86.35
Scraping, CBL-VDL & Hermetical | Changeover Well Volume from WBM to sea water | 2622.3601 | 324.5778 | 8.08 | 0.34 | 86.68
Scraping, CBL-VDL & Hermetical | Carry out Inflow & Hermetical Test | 1 | 0.14286 | 7 | 0.29 | 86.97