## Sheet1
Macro Task | Micro Task | Quantity | Rate (units/hr) | Estimated Time (hr) | Estimated Time (days) | Cumulative Time (days)
BOP & Riser Retrieval / pre rig move | Pull Out Mule Shoe | 2365 | 424.6052 | 5.57 | 0.23 | 0.23
BOP & Riser Retrieval / pre rig move | Lay_Dn_Cement_Head | 1 | 0.7 | 1.43 | 0.06 | 0.29
Pull Out BOP | Rig_up_for_riser_handling | 1 | 0.16566 | 6.04 | 0.25 | 0.54
Pull Out BOP | Unlatch_BOP | 1 | 1 | 1 | 0.04 | 0.58
Pull Out BOP | Secure_Choke_Kill_Boost_Goosenecks | 1 | 0.25 | 4 | 0.17 | 0.75
Pull Out BOP | L_dn_dummy_riser_n_slip_jt | 1 | 0.5 | 2 | 0.08 | 0.83
Pull Out BOP | Tripping_BOP | 78 | 3.1566 | 24.71 | 1.03 | 1.86
Pull Out BOP | Receive_and_Park_BOP | 1 | 0.047619 | 21 | 0.88 | 2.74
Pull Out BOP | Sea_Fasten_Prepare_for_rig_move | 1 | 0.2 | 5 | 0.21 | 2.95
Sail to Well | Sail to Well | 280 | 6.9687 | 40.18 | 1.67 | 4.62
DP Calibration | DP Calibration | 1 | 0.042553 | 23.5 | 0.98 | 5.6
Investigative Hole | Continue RIH 12-1/4'' IH BHA | 1057.5 | 424.6052 | 2.49 | 0.1 | 5.7
Investigative Hole | Drill 12-1/4'' IH Hole | 630 | 28.9714 | 21.75 | 0.91 | 6.61
Investigative Hole | Wiper Trip | 1 | 0.1597 | 6.26 | 0.26 | 6.87
Investigative Hole | Circulation | 602.6118 | 823.0366 | 0.73 | 0.03 | 6.9
Investigative Hole | POOH 12-1/4'' IH BHA | 2745 | 424.6052 | 6.46 | 0.27 | 7.17
Investigative Hole | Slip and Cut | 1 | 0.40126 | 2.49 | 0.1 | 7.28
Jet 36'' Casing | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 7.34
Jet 36'' Casing | Run Conductor Casing | 7 | 0.93961 | 7.45 | 0.31 | 7.65
Jet 36'' Casing | Install_Ball_Valves_Slope_Indicator_Latch_Mud_Mat | 1 | 0.53571 | 1.87 | 0.08 | 7.73
Jet 36'' Casing | Tripping_36_Casing_on_Landing_String | 1485 | 274.3454 | 5.41 | 0.23 | 7.96
Jet 36'' Casing | Tripping_36_Casing_on_Landing_String_OH | 630 | 46.6667 | 13.5 | 0.56 | 8.52
Jet 36'' Casing | Jet Conductor Casing | 1 | 9 | 0.11 | 0 | 8.52
Jet 36'' Casing | Wait on soaking | 1 | 12 | 0.08 | 0 | 8.53
Drill 26'' Hole | Drill 26'' | 550 | 14.3486 | 38.33 | 1.6 | 10.12
Drill 26'' Hole | Wiper Trip | 1 | 0.04143 | 24.14 | 1.01 | 11.13
Drill 26'' Hole | Circulate | 3096.1943 | 1428.5714 | 2.17 | 0.09 | 11.22
Drill 26'' Hole | POOH 26'' BHA | 2745 | 424.6052 | 6.46 | 0.27 | 11.49
Drill 26'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 11.66
Run 20'' Casing & Cement | Rig_up_for_Casing | 1 | 0.44444 | 2.25 | 0.09 | 11.75
Run 20'' Casing & Cement | Run_Check_Float_Fun_20_Casing | 1 | 0.44444 | 2.25 | 0.09 | 11.85
Run 20'' Casing & Cement | Run 20'' Casing | 53 | 3.1364 | 16.9 | 0.7 | 12.55
Run 20'' Casing & Cement | M_Up_HPWHH_Run_Inner_String_Engage_Cart_to_HPWHH | 1 | 0.23529 | 4.25 | 0.18 | 12.73
Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String | 1485 | 206.1859 | 7.2 | 0.3 | 13.03
Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | 630 | 132.7857 | 4.74 | 0.2 | 13.23
Run 20'' Casing & Cement | Cementing 20'' Casing | 1 | 0.16667 | 6 | 0.25 | 13.48
Run 20'' Casing & Cement | Wait on Cement | 1 | 0.083333 | 12 | 0.5 | 13.98
Run 20'' Casing & Cement | Release_Cart_from_HPWHH | 1 | 3.8904 | 0.26 | 0.01 | 13.99
Run 20'' Casing & Cement | POOH Cart Tool to surface | 2115 | 424.6052 | 4.98 | 0.21 | 14.19
BOP Lowering | Rig_up_for_riser_handling | 1 | 0.16566 | 6.04 | 0.25 | 14.45
BOP Lowering | Run_BOP_Splash_Zone | 1 | 0.4 | 2.5 | 0.1 | 14.55
BOP Lowering | Run BOP on Riser | 78 | 3.1566 | 24.71 | 1.03 | 15.58
BOP Lowering | Pressure Test Choke, Kill, Boost & Conduit Lines | 5 | 0.49431 | 10.12 | 0.42 | 16
BOP Lowering | Run_Slip_Jt_Landing_Jt | 1 | 0.36364 | 2.75 | 0.11 | 16.12
BOP Lowering | Install_C_K_B_C_Goosenecks | 1 | 0.4 | 2.5 | 0.1 | 16.22
BOP Lowering | Pressure Test Choke, Kill & Boost Goosenecks | 1 | 0.49431 | 2.02 | 0.08 | 16.3
BOP Lowering | Install_Saddle_Loops_Engage_MRT | 1 | 0.30769 | 3.25 | 0.14 | 16.44
BOP Lowering | Land & Latch BOP. Carry Out Pick up and Slump Test | 1 | 0.66667 | 1.5 | 0.06 | 16.5
BOP Lowering | Pressure Test Connector. Stroke out Slip Jt & Lay Dn Landing Jt | 1 | 0.5 | 2 | 0.08 | 16.59
BOP Lowering | Install_Diverter | 1 | 0.28571 | 3.5 | 0.15 | 16.73
BOP Lowering | Rig Down Spider & Gimbal | 1 | 1 | 1 | 0.04 | 16.77
RIH dumb iron BHA and Carry out LOT | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 16.88
RIH dumb iron BHA and Carry out LOT | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 16.94
RIH dumb iron BHA and Carry out LOT | Surface Equipment Pressure Test | 1 | 0.4 | 2.5 | 0.1 | 17.05
RIH dumb iron BHA and Carry out LOT | Make up Dumb Iron BHA | 1 | 0.21835 | 4.58 | 0.19 | 17.24
RIH dumb iron BHA and Carry out LOT | Run 17-1/2'' BHA | 2695 | 424.6052 | 6.35 | 0.26 | 17.5
RIH dumb iron BHA and Carry out LOT | BOP Pressure Test | 1 | 0.15385 | 6.5 | 0.27 | 17.77
RIH dumb iron BHA and Carry out LOT | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 17.78
RIH dumb iron BHA and Carry out LOT | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 18.4
RIH dumb iron BHA and Carry out LOT | POOH | 2750 | 424.6052 | 6.48 | 0.27 | 18.67
Drill 12.25'' Pilot Hole | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 18.77
Drill 12.25'' Pilot Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 18.84
Drill 12.25'' Pilot Hole | Surface Equipment Pressure Test | 1 | 0.4 | 2.5 | 0.1 | 18.94
Drill 12.25'' Pilot Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 19.13
Drill 12.25'' Pilot Hole | Run 12.25'' BHA | 2695 | 424.6052 | 6.35 | 0.26 | 19.4
Drill 12.25'' Pilot Hole | BOP Pressure Test | 1 | 0.15385 | 6.5 | 0.27 | 19.67
Drill 12.25'' Pilot Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 19.68
Drill 12.25'' Pilot Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 20.3
Drill 12.25'' Pilot Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 20.33
Drill 12.25'' Pilot Hole | Drill 12.25'' | 363 | 7.3928 | 49.1 | 2.05 | 22.37
Drill 12.25'' Pilot Hole | Coring at depth 2915 | 1 | 0.032772 | 30.51 | 1.27 | 23.64
Drill 12.25'' Pilot Hole | POOH | 2755 | 424.6052 | 6.49 | 0.27 | 23.91
Wireline Logging | Wireline Logging | 1 | 0.013889 | 72 | 3 | 26.91
Enlarge Pilot Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 26.98
Enlarge Pilot Hole | Make up MWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 27.17
Enlarge Pilot Hole | Run 17.5'' BHA | 2745 | 424.6052 | 6.46 | 0.27 | 27.44
Enlarge Pilot Hole | Enlarge 12.25'' Hole to 17.5'' | 373 | 31.1233 | 11.98 | 0.5 | 27.94
Enlarge Pilot Hole | Wiper Trip | 1 | 0.2115 | 4.73 | 0.2 | 28.14
Enlarge Pilot Hole | Circulate | 3201.1474 | 1223.9177 | 2.62 | 0.11 | 28.25
Enlarge Pilot Hole | POOH | 3118 | 424.6052 | 7.34 | 0.31 | 28.55
Run 13.375'' Casing & Cement | Retrieve Wear Bush | 1 | 0.083597 | 11.96 | 0.5 | 29.05
Run 13.375'' Casing & Cement | Rig_up_for_Casing | 1 | 0.44444 | 2.25 | 0.09 | 29.14
Run 13.375'' Casing & Cement | Run_Check_Float_Fun_13.625_Casing | 1 | 0.5 | 2 | 0.08 | 29.23
Run 13.375'' Casing & Cement | Run 13.375'' Casing | 84 | 10.8 | 7.78 | 0.32 | 29.55
Run 13.375'' Casing & Cement | Tripping_Casing_on_Landing_String | 2115 | 206.1859 | 10.26 | 0.43 | 29.98
Run 13.375'' Casing & Cement | Land_Latch_Casing_Indexing_Pick_up_test | 1 | 0.26316 | 3.8 | 0.16 | 30.14
Run 13.375'' Casing & Cement | Cementing_13-3/8_in | 1 | 0.125 | 8 | 0.33 | 30.47
Run 13.375'' Casing & Cement | Set_Seal_Assembly | 1 | 0.57143 | 1.75 | 0.07 | 30.54
Run 13.375'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | 1 | 0.66667 | 1.5 | 0.06 | 30.61
Run 13.375'' Casing & Cement | POOH PADPRT to surface | 2115 | 424.6052 | 4.98 | 0.21 | 30.81
Run 13.375'' Casing & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 30.92
Run 13.375'' Casing & Cement | Set Wear Bush at Wellhead | 1 | 0.083597 | 11.96 | 0.5 | 31.42
Drill 12.25'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 31.48
Drill 12.25'' Hole | Lay_Dn_Cement_Head | 1 | 0.7 | 1.43 | 0.06 | 31.54
Drill 12.25'' Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 31.73
Drill 12.25'' Hole | Run 12.25'' BHA | 2818 | 424.6052 | 6.64 | 0.28 | 32.01
Drill 12.25'' Hole | BOP_Function_Test | 1 | 1.6667 | 0.6 | 0.03 | 32.04
Drill 12.25'' Hole | Choke_Drill | 1 | 0.8 | 1.25 | 0.05 | 32.09
Drill 12.25'' Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 32.1
Drill 12.25'' Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 32.71
Drill 12.25'' Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 32.74
Drill 12.25'' Hole | Drill 12.25'' | 797 | 7.3928 | 107.81 | 4.49 | 37.24
Drill 12.25'' Hole | Coring at depth 3635 | 1 | 0.023575 | 42.42 | 1.77 | 39
Drill 12.25'' Hole | wiper_trip | 1 | 0.097781 | 10.23 | 0.43 | 39.43
Drill 12.25'' Hole | Circulate | 2933.5594 | 823.0366 | 3.56 | 0.15 | 39.58
Drill 12.25'' Hole | POOH 12.25'' BHA to casing shoe | 807 | 144.6351 | 5.58 | 0.23 | 39.81
Drill 12.25'' Hole | POOH 12.25'' BHA to surface | 2818 | 424.6052 | 6.64 | 0.28 | 40.09
Drill 12.25'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 40.26
Wireline Logging | Wireline Logging | 1 | 0.010417 | 96 | 4 | 44.26
Wireline Logging | Roundtrip for logging | 1 | 0.067639 | 14.78 | 0.62 | 44.87
Wireline Logging | Wireline_Logging_part_2 | 1 | 0.010417 | 96 | 4 | 48.87
Run 9-5/8'' Casing & Cement | Roundtrip for Casing Lowering | 1 | 0.067639 | 14.78 | 0.62 | 49.49
Run 9-5/8'' Casing & Cement | Retrieve Wear Bush | 1 | 0.083597 | 11.96 | 0.5 | 49.99
Run 9-5/8'' Casing & Cement | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 50.05
Run 9-5/8'' Casing & Cement | Run_Check_Float_Fun_9.625_Casing | 1 | 0.5 | 2 | 0.08 | 50.14
Run 9-5/8'' Casing & Cement | Run 9-5/8'' Casing | 151 | 10.8 | 13.98 | 0.58 | 50.72
Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String | 1308 | 206.1859 | 6.34 | 0.26 | 50.98
Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | 807 | 132.7857 | 6.08 | 0.25 | 51.24
Run 9-5/8'' Casing & Cement | Cementing_9-5/8_in | 1 | 0.125 | 8 | 0.33 | 51.57
Run 9-5/8'' Casing & Cement | Set_Seal_Assembly | 1 | 0.57143 | 1.75 | 0.07 | 51.64
Run 9-5/8'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | 1 | 0.66667 | 1.5 | 0.06 | 51.71
Run 9-5/8'' Casing & Cement | POOH PADPRT to surface | 2115 | 424.6052 | 4.98 | 0.21 | 51.91
Run 9-5/8'' Casing & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 52.02
Run 9-5/8'' Casing & Cement | Set Wear Bush at Wellhead | 1 | 0.083597 | 11.96 | 0.5 | 52.52
Drill 8.5'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 52.58
Drill 8.5'' Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 52.77
Drill 8.5'' Hole | Run 8.5'' BHA | 3625 | 424.6052 | 8.54 | 0.36 | 53.13
Drill 8.5'' Hole | BOP_Pressure_Test | 1 | 0.15385 | 6.5 | 0.27 | 53.4
Drill 8.5'' Hole | Choke_Drill | 1 | 0.8 | 1.25 | 0.05 | 53.45
Drill 8.5'' Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 53.46
Drill 8.5'' Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 54.08
Drill 8.5'' Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 54.11
Drill 8.5'' Hole | Drill 8.5'' | 1090 | 7.3928 | 147.44 | 6.14 | 60.25
Drill 8.5'' Hole | Coring at depth 4275 | 1 | 0.020044 | 49.89 | 2.08 | 62.33
Drill 8.5'' Hole | Coring at depth 4925 | 1 | 0.018565 | 53.86 | 2.24 | 64.58
Drill 8.5'' Hole | wiper_trip | 1 | 0.055004 | 18.18 | 0.76 | 65.33
Drill 8.5'' Hole | Circulate | 2622.3601 | 288.5136 | 9.09 | 0.38 | 65.71
Drill 8.5'' Hole | POOH 12.25'' BHA to casing shoe | 1100 | 144.6351 | 7.61 | 0.32 | 66.03
Drill 8.5'' Hole | POOH 12.25'' BHA to surface | 3625 | 424.6052 | 8.54 | 0.36 | 66.38
Drill 8.5'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 66.56
Wireline Logging | Basic Logs | 1 | 0.010417 | 96 | 4 | 70.56
Wireline Logging | Roundtrip for logging | 1 | 0.053929 | 18.54 | 0.77 | 71.33
Wireline Logging | Advance_Logging | 1 | 0.010417 | 96 | 4 | 75.33
Run 7'' Liner & Cement | Roundtrip for Casing Lowering | 1 | 0.053929 | 18.54 | 0.77 | 76.1
Run 7'' Liner & Cement | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 76.17
Run 7'' Liner & Cement | Run_Check_Float_Fun_7''_Liner | 1 | 0.5 | 2 | 0.08 | 76.25
Run 7'' Liner & Cement | Run 7'' Liner | 105 | 10.8 | 9.72 | 0.41 | 76.66
Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String | 2675 | 206.1859 | 12.97 | 0.54 | 77.2
Run 7'' Liner & Cement | Tripping_Casing_on_Landing_String_OH | 1100 | 132.7857 | 8.28 | 0.35 | 77.54
Run 7'' Liner & Cement | Cementing_7'' Liner | 1 | 0.125 | 8 | 0.33 | 77.88
Run 7'' Liner & Cement | Set_Liner_Hanger_Seal | 1 | 0.57143 | 1.75 | 0.07 | 77.95
Run 7'' Liner & Cement | Release_Liner_Hanger_Running_Tool | 1 | 0.66667 | 1.5 | 0.06 | 78.01
Run 7'' Liner & Cement | POOH Liner Hanger Running Tool to surface | 2115 | 424.6052 | 4.98 | 0.21 | 78.22
Run 7'' Liner & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 78.32
Scraping, CBL-VDL & Hermetical | RIH Tandem Scraper from surface to Scraping depth | 3425 | 424.6052 | 8.07 | 0.34 | 78.66
Scraping, CBL-VDL & Hermetical | Scrape Casing | 1600 | 144.6351 | 11.06 | 0.46 | 79.12
Scraping, CBL-VDL & Hermetical | POOH Tandem Scraping BHA | 5025 | 424.6052 | 11.83 | 0.49 | 79.61
Scraping, CBL-VDL & Hermetical | Record CBL VDL Log | 1 | 0.041667 | 24 | 1 | 80.61
Scraping, CBL-VDL & Hermetical | Run Mule Shoe for hermetical and inflow test | 5025 | 424.6052 | 11.83 | 0.49 | 81.11
Scraping, CBL-VDL & Hermetical | Changeover Well Volume from WBM to sea water | 2622.3601 | 324.5778 | 8.08 | 0.34 | 81.44
Scraping, CBL-VDL & Hermetical | Carry out Inflow & Hermetical Test | 1 | 0.14286 | 7 | 0.29 | 81.73