## Sheet1
Macro Task | Micro Task | Quantity | Rate (units/hr) | Estimated Time (hr) | Estimated Time (days) | Cumulative Time (days)
BOP & Riser Retrieval / pre rig move | Pull Out Mule Shoe | 1315 | 424.6052 | 3.1 | 0.13 | 0.13
BOP & Riser Retrieval / pre rig move | Lay_Dn_Cement_Head | 1 | 0.7 | 1.43 | 0.06 | 0.19
Pull Out BOP | Rig_up_for_riser_handling | 1 | 0.16566 | 6.04 | 0.25 | 0.44
Pull Out BOP | Unlatch_BOP | 1 | 1 | 1 | 0.04 | 0.48
Pull Out BOP | Secure_Choke_Kill_Boost_Goosenecks | 1 | 0.25 | 4 | 0.17 | 0.65
Pull Out BOP | L_dn_dummy_riser_n_slip_jt | 1 | 0.5 | 2 | 0.08 | 0.73
Pull Out BOP | Tripping_BOP | 39 | 3.1566 | 12.35 | 0.51 | 1.25
Pull Out BOP | Receive_and_Park_BOP | 1 | 0.047619 | 21 | 0.88 | 2.12
Pull Out BOP | Sea_Fasten_Prepare_for_rig_move | 1 | 0.2 | 5 | 0.21 | 2.33
Sail to Well | Sail to Well | 280 | 6.9687 | 40.18 | 1.67 | 4
DP Calibration | DP Calibration | 1 | 0.042553 | 23.5 | 0.98 | 4.98
Investigative Hole | Continue RIH 12-1/4'' IH BHA | 532.5 | 424.6052 | 1.25 | 0.05 | 5.04
Investigative Hole | Drill 12-1/4'' IH Hole | 400 | 28.9714 | 13.81 | 0.58 | 5.61
Investigative Hole | Wiper Trip | 1 | 0.25453 | 3.93 | 0.16 | 5.77
Investigative Hole | Circulation | 382.6107 | 823.0366 | 0.46 | 0.02 | 5.79
Investigative Hole | POOH 12-1/4'' IH BHA | 1465 | 424.6052 | 3.45 | 0.14 | 5.94
Investigative Hole | Slip and Cut | 1 | 0.40126 | 2.49 | 0.1 | 6.04
Jet 36'' Casing | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 6.11
Jet 36'' Casing | Run Conductor Casing | 7 | 0.93961 | 7.45 | 0.31 | 6.42
Jet 36'' Casing | Install_Ball_Valves_Slope_Indicator_Latch_Mud_Mat | 1 | 0.53571 | 1.87 | 0.08 | 6.5
Jet 36'' Casing | Tripping_36_Casing_on_Landing_String | 665 | 274.3454 | 2.42 | 0.1 | 6.6
Jet 36'' Casing | Tripping_36_Casing_on_Landing_String_OH | 400 | 46.6667 | 8.57 | 0.36 | 6.95
Jet 36'' Casing | Jet Conductor Casing | 1 | 9 | 0.11 | 0 | 6.96
Jet 36'' Casing | Wait on soaking | 1 | 12 | 0.08 | 0 | 6.96
Drill 26'' Hole | Drill 26'' | 320 | 14.3486 | 22.3 | 0.93 | 7.89
Drill 26'' Hole | Wiper Trip | 1 | 0.07839 | 12.76 | 0.53 | 8.42
Drill 26'' Hole | Circulate | 1927.2155 | 1428.5714 | 1.35 | 0.06 | 8.48
Drill 26'' Hole | POOH 26'' BHA | 1465 | 424.6052 | 3.45 | 0.14 | 8.62
Drill 26'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 8.79
Run 20'' Casing & Cement | Rig_up_for_Casing | 1 | 0.44444 | 2.25 | 0.09 | 8.89
Run 20'' Casing & Cement | Run_Check_Float_Fun_20_Casing | 1 | 0.44444 | 2.25 | 0.09 | 8.98
Run 20'' Casing & Cement | Run 20'' Casing | 34 | 3.1364 | 10.84 | 0.45 | 9.43
Run 20'' Casing & Cement | M_Up_HPWHH_Run_Inner_String_Engage_Cart_to_HPWHH | 1 | 0.23529 | 4.25 | 0.18 | 9.61
Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String | 665 | 206.1859 | 3.23 | 0.13 | 9.74
Run 20'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | 400 | 132.7857 | 3.01 | 0.13 | 9.87
Run 20'' Casing & Cement | Cementing 20'' Casing | 1 | 0.16667 | 6 | 0.25 | 10.12
Run 20'' Casing & Cement | Wait on Cement | 1 | 0.083333 | 12 | 0.5 | 10.62
Run 20'' Casing & Cement | Release_Cart_from_HPWHH | 1 | 3.8904 | 0.26 | 0.01 | 10.63
Run 20'' Casing & Cement | POOH Cart Tool to surface | 1065 | 424.6052 | 2.51 | 0.1 | 10.74
BOP Lowering | Rig_up_for_riser_handling | 1 | 0.16566 | 6.04 | 0.25 | 10.99
BOP Lowering | Run_BOP_Splash_Zone | 1 | 0.4 | 2.5 | 0.1 | 11.09
BOP Lowering | Run BOP on Riser | 39 | 3.1566 | 12.35 | 0.51 | 11.61
BOP Lowering | Pressure Test Choke, Kill, Boost & Conduit Lines | 3 | 0.49431 | 6.07 | 0.25 | 11.86
BOP Lowering | Run_Slip_Jt_Landing_Jt | 1 | 0.36364 | 2.75 | 0.11 | 11.97
BOP Lowering | Install_C_K_B_C_Goosenecks | 1 | 0.4 | 2.5 | 0.1 | 12.08
BOP Lowering | Pressure Test Choke, Kill & Boost Goosenecks | 1 | 0.49431 | 2.02 | 0.08 | 12.16
BOP Lowering | Install_Saddle_Loops_Engage_MRT | 1 | 0.30769 | 3.25 | 0.14 | 12.3
BOP Lowering | Land & Latch BOP. Carry Out Pick up and Slump Test | 1 | 0.66667 | 1.5 | 0.06 | 12.36
BOP Lowering | Pressure Test Connector. Stroke out Slip Jt & Lay Dn Landing Jt | 1 | 0.5 | 2 | 0.08 | 12.44
BOP Lowering | Install_Diverter | 1 | 0.28571 | 3.5 | 0.15 | 12.59
BOP Lowering | Rig Down Spider & Gimbal | 1 | 1 | 1 | 0.04 | 12.63
Drill 17.5'' Hole | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 12.73
Drill 17.5'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 12.8
Drill 17.5'' Hole | Surface Equipment Pressure Test | 1 | 0.4 | 2.5 | 0.1 | 12.91
Drill 17.5'' Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 13.1
Drill 17.5'' Hole | Run 17-1/2'' BHA | 1415 | 424.6052 | 3.33 | 0.14 | 13.24
Drill 17.5'' Hole | BOP Pressure Test | 1 | 0.15385 | 6.5 | 0.27 | 13.51
Drill 17.5'' Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 13.51
Drill 17.5'' Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 14.13
Drill 17.5'' Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 14.16
Drill 17.5'' Hole | Drill 17.5'' | 35 | 10.3744 | 3.37 | 0.14 | 14.3
Drill 17.5'' Hole | Wiper Trip | 1 | 0.92286 | 1.08 | 0.05 | 14.35
Drill 17.5'' Hole | Circulate | 1562.0587 | 1223.9177 | 1.28 | 0.05 | 14.4
Drill 17.5'' Hole | POOH | 1500 | 424.6052 | 3.53 | 0.15 | 14.55
Wireline Logging | Wireline Logging | 1 | 0.013889 | 72 | 3 | 17.55
Run 13.375'' Casing & Cement | Retrieve Wear Bush | 1 | 0.14252 | 7.02 | 0.29 | 17.84
Run 13.375'' Casing & Cement | Rig_up_for_Casing | 1 | 0.44444 | 2.25 | 0.09 | 17.93
Run 13.375'' Casing & Cement | Run_Check_Float_Fun_13.625_Casing | 1 | 0.5 | 2 | 0.08 | 18.02
Run 13.375'' Casing & Cement | Run 13.375'' Casing | 37 | 10.8 | 3.43 | 0.14 | 18.16
Run 13.375'' Casing & Cement | Tripping_Casing_on_Landing_String | 1065 | 206.1859 | 5.17 | 0.22 | 18.38
Run 13.375'' Casing & Cement | Land_Latch_Casing_Indexing_Pick_up_test | 1 | 0.26316 | 3.8 | 0.16 | 18.53
Run 13.375'' Casing & Cement | Cementing_13-3/8_in | 1 | 0.125 | 8 | 0.33 | 18.87
Run 13.375'' Casing & Cement | Set_Seal_Assembly | 1 | 0.57143 | 1.75 | 0.07 | 18.94
Run 13.375'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | 1 | 0.66667 | 1.5 | 0.06 | 19
Run 13.375'' Casing & Cement | POOH PADPRT to surface | 1065 | 424.6052 | 2.51 | 0.1 | 19.11
Run 13.375'' Casing & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 19.21
Run 13.375'' Casing & Cement | Set Wear Bush at Wellhead | 1 | 0.14252 | 7.02 | 0.29 | 19.5
Drill 12.25'' Hole | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 19.57
Drill 12.25'' Hole | Lay_Dn_Cement_Head | 1 | 0.7 | 1.43 | 0.06 | 19.63
Drill 12.25'' Hole | Make up LWD BHA | 1 | 0.21835 | 4.58 | 0.19 | 19.82
Drill 12.25'' Hole | Run 12.25'' BHA | 1200 | 424.6052 | 2.83 | 0.12 | 19.94
Drill 12.25'' Hole | BOP_Function_Test | 1 | 1.6667 | 0.6 | 0.03 | 19.96
Drill 12.25'' Hole | Choke_Drill | 1 | 0.8 | 1.25 | 0.05 | 20.02
Drill 12.25'' Hole | Continue RIH with Wash Dn & Tag Cement | 30 | 147 | 0.2 | 0.01 | 20.02
Drill 12.25'' Hole | Drill_Shoe_Track_LOT | 1 | 0.067608 | 14.79 | 0.62 | 20.64
Drill 12.25'' Hole | Fingerprint_Flow_Back | 1 | 1.3333 | 0.75 | 0.03 | 20.67
Drill 12.25'' Hole | Drill 12.25'' | 290 | 7.3928 | 39.23 | 1.63 | 22.31
Drill 12.25'' Hole | Coring at depth 1600 | 1 | 0.04659 | 21.46 | 0.89 | 23.2
Drill 12.25'' Hole | wiper_trip | 1 | 0.23879 | 4.19 | 0.17 | 23.38
Drill 12.25'' Hole | Circulate | 1408.9101 | 823.0366 | 1.71 | 0.07 | 23.45
Drill 12.25'' Hole | POOH 12.25'' BHA to casing shoe | 300 | 144.6351 | 2.07 | 0.09 | 23.53
Drill 12.25'' Hole | POOH 12.25'' BHA to surface | 1200 | 424.6052 | 2.83 | 0.12 | 23.65
Drill 12.25'' Hole | Break Off BHA | 1 | 0.24399 | 4.1 | 0.17 | 23.82
Wireline Logging | Wireline Logging | 1 | 0.010417 | 96 | 4 | 27.82
Wireline Logging | Roundtrip for logging | 1 | 0.13691 | 7.3 | 0.3 | 28.13
Wireline Logging | Wireline_Logging_part_2 | 1 | 0.010417 | 96 | 4 | 32.13
Run 9-5/8'' Casing & Cement | Roundtrip for Casing Lowering | 1 | 0.13691 | 7.3 | 0.3 | 32.43
Run 9-5/8'' Casing & Cement | Retrieve Wear Bush | 1 | 0.14252 | 7.02 | 0.29 | 32.72
Run 9-5/8'' Casing & Cement | Change_Pipe_Handler | 1 | 0.6219 | 1.61 | 0.07 | 32.79
Run 9-5/8'' Casing & Cement | Run_Check_Float_Fun_9.625_Casing | 1 | 0.5 | 2 | 0.08 | 32.87
Run 9-5/8'' Casing & Cement | Run 9-5/8'' Casing | 62 | 10.8 | 5.74 | 0.24 | 33.11
Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String | 765 | 206.1859 | 3.71 | 0.15 | 33.27
Run 9-5/8'' Casing & Cement | Tripping_Casing_on_Landing_String_OH | 300 | 132.7857 | 2.26 | 0.09 | 33.36
Run 9-5/8'' Casing & Cement | Cementing_9-5/8_in | 1 | 0.125 | 8 | 0.33 | 33.69
Run 9-5/8'' Casing & Cement | Set_Seal_Assembly | 1 | 0.57143 | 1.75 | 0.07 | 33.77
Run 9-5/8'' Casing & Cement | Release_PADPRT_L_Dn_Cement_Head | 1 | 0.66667 | 1.5 | 0.06 | 33.83
Run 9-5/8'' Casing & Cement | POOH PADPRT to surface | 1065 | 424.6052 | 2.51 | 0.1 | 33.93
Run 9-5/8'' Casing & Cement | slip_and_cut | 1 | 0.40126 | 2.49 | 0.1 | 34.04
Run 9-5/8'' Casing & Cement | Set Wear Bush at Wellhead | 1 | 0.14252 | 7.02 | 0.29 | 34.33
Scraping, CBL-VDL & Hermetical | RIH Tandem Scraper from surface to Scraping depth | 1300 | 424.6052 | 3.06 | 0.13 | 34.46
Scraping, CBL-VDL & Hermetical | Scrape Casing | 500 | 144.6351 | 3.46 | 0.14 | 34.6
Scraping, CBL-VDL & Hermetical | POOH Tandem Scraping BHA | 1800 | 424.6052 | 4.24 | 0.18 | 34.78
Scraping, CBL-VDL & Hermetical | Record CBL VDL Log | 1 | 0.041667 | 24 | 1 | 35.78
Scraping, CBL-VDL & Hermetical | Run Mule Shoe for hermetical and inflow test | 1800 | 424.6052 | 4.24 | 0.18 | 35.96
Scraping, CBL-VDL & Hermetical | Changeover Well Volume from WBM to sea water | 1222.3927 | 324.5778 | 3.77 | 0.16 | 36.11
Scraping, CBL-VDL & Hermetical | Carry out Inflow & Hermetical Test | 1 | 0.14286 | 7 | 0.29 | 36.4